## NDIS Template
Status | Task | Supplier | Approx Date | confirm | supplier_confirm | Task Started | Completed | Paid Internal | Start | A Start Date | Complete | A Complete Date | duration | supplier_category | Critical Path | Predecessors | Allocation %
Not Started | ORDER - Soil Test and Wind Rating | Sophie Harder | [6 empty] | 2024-08-07 |  | 2024-08-13 |  | 5d | ADMIN | Not Critical
Not Started | ORDER - Contour Survey Plan | Sophie Harder | [6 empty] | 2024-08-07 |  | 2024-08-13 |  | 5d | ADMIN | Not Critical
Not Started | DO - Request Full Ghost Siting | Sophie Harder | [6 empty] | 2024-08-14 |  | 2024-08-14 |  | 1d | ADMIN | Critical | 1, 2
Not Started | DO - Covenant Approval (if required) | Sophie Harder | [6 empty] | 2024-08-15 |  | 2024-08-15 |  | 1d | ADMIN | Not Critical | 1, 2, 3
Not Started | CONFIRM - Price for ADH | Sam Harder | [6 empty] | 2024-08-16 |  | 2024-08-16 |  | 1d | ADMIN | Critical | 3, 4
Not Started | SIGN - CPN | Andrew Clement | [6 empty] | 2024-08-19 |  | 2024-08-19 |  | 1d | SUPERVISOR | Critical | 5
Not Started | CREATE - Contracts | Sophie Harder | [6 empty] | 2024-08-20 |  | 2024-08-20 |  | 1d | ADMIN | Critical | 6
Not Started | DO - Load Invoices into XERO | Sophie Harder | [6 empty] | 2024-08-21 |  | 2024-08-21 |  | 1d | ADMIN | Not Critical | 7
Not Started | GET - Finance Approval | Sophie Harder | [6 empty] | 2024-08-21 |  | 2024-09-18 |  | 21d | ADMIN | Critical | 7
Not Started | DO - Plumbing Approval | Sophie Harder | [6 empty] | 2024-09-19 |  | 2024-09-19 |  | 1d | ADMIN | Not Critical | 9
Not Started | DO - QLeave | Sophie Harder | [6 empty] | 2024-09-19 |  | 2024-09-19 |  | 1d | ADMIN | Not Critical | 9
Not Started | DO - Slab Design | Sophie Harder | [6 empty] | 2024-09-19 |  | 2024-09-19 |  | 1d | ADMIN | Not Critical | 9
Not Started | DO - Hydraulics Design | Sophie Harder | [6 empty] | 2024-09-19 |  | 2024-09-19 |  | 1d | ADMIN | Not Critical | 9
Not Started | DO - Energy Efficiency | Sophie Harder | [6 empty] | 2024-09-19 |  | 2024-09-19 |  | 1d | ADMIN | Not Critical | 9
Not Started | CHECK - Land Settlement | Sophie Harder | [6 empty] | 2024-09-19 |  | 2024-09-19 |  | 1d | ADMIN | Not Critical | 9
Not Started | DO - Certification | Sophie Harder | [6 empty] | 2024-09-20 |  | 2024-10-03 |  | 10d | ADMIN | Critical | 10, 11, 12, 13, 14
Not Started | CLAIM - Deposit | Sophie Harder | [6 empty] | 2024-09-20 |  | 2024-09-26 |  | 5d | ADMIN | Critical | 15
Not Started | DO - Driveway Application | Sophie Harder | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | ADMIN | Not Critical | 16
Not Started | ORDER - Trusses | Sam Harder | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | ADMIN | Not Critical | 15, 16
Not Started | ORDER - Window Actuators | Sam Harder | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | ADMIN | Not Critical | 15, 16
Not Started | ORDER - Kitchen Parts | Sam Harder | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | ADMIN | Not Critical | 15, 16
Not Started | ORDER - Door Automation | Sam Harder | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | ADMIN | Not Critical | 15, 16
Not Started | ORDER - Plumbing Items | Sam Harder | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | ADMIN | Not Critical | 15, 16
Not Started | ORDER - Frame | Sam Harder | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | ADMIN | Not Critical | 15, 16
Not Started | ORDER - Roof | Sam Harder | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | ADMIN | Not Critical | 15, 16
Not Started | ORDER - EXT Doors | Sam Harder | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | ADMIN | Not Critical | 15, 16
Not Started | ORDER - Surveyor | Sam Harder | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | ADMIN | Not Critical | 15, 16
Not Started | ORDER - Windows | Sam Harder | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | ADMIN | Not Critical | 15, 16
Not Started | Order SDA Auto Desk Stand For Kitchen | Tekna Admin | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d |  |  | 15, 16
Not Started | Order SDA Manual Adjustable Desks Kitchen | Tekna Admin | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d |  |  | 15, 16
Not Started | Req Site Cut | Tekna Site | [6 empty] | 2024-10-04 |  | 2024-10-04 |  | 1d | SITE WORKS | Critical | 15, 16
Not Started | SLAB | [7 empty] | 2024-10-07 |  | 2024-10-22 |  | 12d |  | Not Critical
Not Started | Req Surveyor to Setout Wafflepod | Survey Mark | [6 empty] | 2024-10-07 |  | 2024-10-07 |  | 1d | SURVEYOR | Not Critical | 31
Not Started | Req Drainer for Drains Wafflepod | Plumber | [6 empty] | 2024-10-08 |  | 2024-10-09 |  | 2d | PLUMBER | Not Critical | 33
Not Started | Req Electrician Underground (INC NBN) | Electrican | [6 empty] | 2024-10-08 |  | 2024-10-08 |  | 1d | ELECTRICAL | Not Critical | 34SS
Not Started | Req Power To Site | Sophie Harder | [6 empty] | 2024-10-09 |  | 2024-10-22 |  | 10d | ADMIN | Not Critical | 35
Not Started | DO - Formwork for Courtyard Seat | Tekna Finishing Touches | [6 empty] | 2024-10-10 |  | 2024-10-10 |  | 1d | CARPENTER | Not Critical | 38SS
Not Started | Req Concreter For Complete Slab Labour And Materials | JND Concrete | [6 empty] | 2024-10-10 |  | 2024-10-11 |  | 2d | CONCRETOR | Critical | 33, 34, 35
Not Started | Req Termite Protection Penetrations | Bittn Australia PTY Ltd | [6 empty] | 2024-10-10 |  | 2024-10-10 |  | 1d | TERMITE PROTECTION | Not Critical | 38SS
Not Started | DO - Fill with Concrete Courtyard Seat | Tekna Finishing Touches | [6 empty] | 2024-10-11 |  | 2024-10-11 |  | 1d | CARPENTER | Not Critical | 38FF
Not Started | PHOTO - Slab | Andrew Clement | [6 empty] | 2024-10-14 |  | 2024-10-14 |  | 1d | SUPERVISOR | Not Critical | 38
Not Started | CERTIFICATE - 12 Form 43 - Stormwater Installation | Sophie Harder | [6 empty] | 2024-10-23 |  | 2024-10-23 |  | 1d | ADMIN | Not Critical | 32
| Admin | [7 empty] | 2024-10-07 |  | 2024-10-07 |  | 1d |  |  | 31
Not Started | Pay Coaching Fee | Tekna Admin | [6 empty] | 2024-10-07 |  | 2024-10-07 |  | 1d |  |  |  | 100%
Not Started | Pay Franchise Fee | Tekna Admin | [6 empty] | 2024-10-07 |  | 2024-10-07 |  | 1d |  |  |  | 100%
Not Started | Pay Franchise Marketing Fee | Tekna Admin | [6 empty] | 2024-10-07 |  | 2024-10-07 |  | 1d |  |  |  | 100%
Not Started | Pay Overhead Fee | Tekna Admin | [6 empty] | 2024-10-07 |  | 2024-10-07 |  | 1d |  |  |  | 100%
Not Started | Pay Supervisor Fee | Tekna Admin | [6 empty] | 2024-10-07 |  | 2024-10-07 |  | 1d |  |  |  | 100%
Not Started | Req 3D Drafting Qtys and Certification | Tekna Admin | [6 empty] | 2024-10-07 |  | 2024-10-07 |  | 1d |  |  |  | 100%
Not Started | Req Soil Removal | Tekna Site | [6 empty] | 2024-10-07 |  | 2024-10-07 |  | 1d |  |  | 31
Not Started | CLAIM - Slab | Sophie Harder | [6 empty] | 2024-10-14 |  | 2024-10-18 |  | 5d | ADMIN | Critical | 38
Not Started | Req Waterproof Slab Edge | Tekna Finishing Touches | [6 empty] | 2024-10-14 |  | 2024-10-14 |  | 1d | CARPENTER | Not Critical | 38
Not Started | DO - Strip Formwork for Courtyard Seat | Tekna Finishing Touches | [6 empty] | 2024-10-14 |  | 2024-10-14 |  | 1d | CARPENTER | Not Critical | 38
Not Started | FRAME | [7 empty] | 2024-10-15 |  | 2024-10-31 |  | 13d |  | Not Critical
Not Started | Req Frame Hardware | Bunnings | [6 empty] | 2024-10-15 |  | 2024-10-15 |  | 1d | TIMBER FRAME | Not Critical | 57SS -1d
Not Started | Req Frame Material Ground Floor | Bunnings | [6 empty] | 2024-10-15 |  | 2024-10-15 |  | 1d | TIMBER FRAME | Not Critical | 57SS -1d
Not Started | Req Carpenter Ground Floor | Tekna Carpentry | [6 empty] | 2024-10-16 |  | 2024-10-22 |  | 5d | CARPENTER | Critical | 38FS +2d
Not Started | Req Termite Perimeter | Bittn Australia PTY Ltd | [6 empty] | 2024-10-16 |  | 2024-10-16 |  | 1d | TERMITE PROTECTION | Not Critical | 57SS
Not Started | Req Roof Trusses | Bunnings | [6 empty] | 2024-10-18 |  | 2024-10-18 |  | 1d | TRUSSES | Not Critical | 57SS +2d
Not Started | Req Crane Roof Trusses | Crane | [6 empty] | 2024-10-18 |  | 2024-10-18 |  | 1d | CRANE | Not Critical | 59SS
Not Started | Req Steel Posts | Harveys Towing | [6 empty] | 2024-10-21 |  | 2024-10-21 |  | 1d | STEEL BEAMS/POSTS | Not Critical | 59
Not Started | PHOTO - Frame | Andrew Clement | [6 empty] | 2024-10-23 |  | 2024-10-23 |  | 1d | SUPERVISOR | Not Critical | 57
Not Started | Do Frame Inspection | Andrew Clement | [6 empty] | 2024-10-23 |  | 2024-10-23 |  | 1d | ENGINEER | Not Critical | 57
Not Started | Req Partition Wall | [7 empty] | 2024-10-23 |  | 2024-10-23 |  | 1d | PARTITION WALL | Not Critical | 57
Not Started | CERTIFICATE - 05 Form 43 - Termite Installation Part B | Sophie Harder | [6 empty] | 2024-10-24 |  | 2024-10-24 |  | 1d | ADMIN | Not Critical | 58FS +5d
Not Started | CLAIM - Frame | Sophie Harder | [6 empty] | 2024-10-24 |  | 2024-10-30 |  | 5d | ADMIN | Critical | 57, 62
Not Started | CERTIFICATE - 04 Form 15 Truss Layout Plan | Sophie Harder | [6 empty] | 2024-10-28 |  | 2024-10-28 |  | 1d | ADMIN | Not Critical | 59FS +5d
Not Started | CERTIFICATE - Engineer Frame INC Hoist | Sophie Harder | [6 empty] | 2024-10-31 |  | 2024-10-31 |  | 1d | ADMIN | Not Critical | 63FS +5d
Not Started | CERTIFICATE - 01 Form 12 - Surveyor Setout | Sophie Harder | [6 empty] | 2024-10-22 |  | 2024-10-22 |  | 1d | ADMIN | Not Critical | 33FS +10d
Not Started | CERTIFICATE - 02 Form 43 - Termite Installation Part A | Sophie Harder | [6 empty] | 2024-10-30 |  | 2024-10-30 |  | 1d |  |  | 32FS +5d
Not Started | Req Level Site After Slab Poured Soil Removal | Tekna Site | [6 empty] | 2024-10-23 |  | 2024-10-23 |  | 1d |  |  | 32
Not Started | ENCLOSED | [7 empty] | 2024-10-24 |  | 2024-11-19 |  | 19d |  | Not Critical
Not Started | Req Fascia and Gutter and Colorbond Roof | Joii Roofing | [6 empty] | 2024-10-24 |  | 2024-10-30 |  | 5d | ROOF | Critical | 57, 64
| CERTIFICATION - 07 Form 43 - Roof Insulation | Sophie Harder | [6 empty] | 2024-11-14 |  | 2024-11-14 |  | 1d |  |  | 73FS +10d
Not Started | Req External Doors | Prehung Doors | [6 empty] | 2024-10-29 |  | 2024-10-29 |  | 1d | ENT DOORS | Not Critical | 73FF -1d
Not Started | Req Windows | Southern Star Windows | [6 empty] | 2024-10-29 |  | 2024-10-29 |  | 1d | WINDOWS | Not Critical | 73FF -1d
Not Started | Req External Door Handle Locks | Prehung Doors | [6 empty] | 2024-10-29 |  | 2024-10-29 |  | 1d | ENT DOORS | Not Critical | 75SS
Not Started | Req Carpenter Install Windows/Doors | Tekna Carpentry | [6 empty] | 2024-10-30 |  | 2024-10-30 |  | 1d | CARPENTER | Not Critical | 57, 64, 76
Not Started | Req Carpenter Straighten Frame | Tekna Carpentry | [6 empty] | 2024-10-30 |  | 2024-10-30 |  | 1d | CARPENTER | Not Critical | 78SS
Not Started | Req Mixer Bodies For Plumber Rough In | Harvey Norman Commerical - Plumbing | [6 empty] | 2024-10-30 |  | 2024-10-30 |  | 1d | PLUMBING FITOFF GEAR | Not Critical | 88SS -1d
Not Started | FIT - Window Actuators | Tekna Finishing Touches | [6 empty] | 2024-10-30 |  | 2024-10-30 |  | 1d | CARPENTER | Not Critical | 76, 78SS
Not Started | Req Wall Sisilation Ground Floor | Austral Insulation | [6 empty] | 2024-10-30 |  | 2024-10-30 |  | 1d | INSULATION | Not Critical | 78SS
Not Started | Req Site Clean After Roof | Tekna Site | [6 empty] | 2024-10-31 |  | 2024-10-31 |  | 1d |  |  | 73
Not Started | Req Measure Garage Doors | Sunstate Garage Doors | [6 empty] | 2024-10-31 |  | 2024-10-31 |  | 1d | GARAGE DOORS | Not Critical | 78
Not Started | Req Rough In Solar Panels | Open Electrical | [6 empty] | 2024-10-31 |  | 2024-10-31 |  | 1d | SOLAR | Not Critical | 73
Not Started | Req Air Conditioning Rough In | Star Airconditioning | [6 empty] | 2024-10-31 |  | 2024-10-31 |  | 1d | AIR CONDITIONING | Not Critical | 73
Not Started | Req Electrician - Prewire | Electrican | [6 empty] | 2024-10-31 |  | 2024-11-04 |  | 3d | ELECTRICAL | Not Critical | 73
Not Started | Req Plumber Rough In | Plumber | [6 empty] | 2024-10-31 |  | 2024-11-04 |  | 3d | PLUMBER | Not Critical | 73
Not Started | Req Soffit Hardware and Cladding | Bunnings | [6 empty] | 2024-10-31 |  | 2024-10-31 |  | 1d | SOFFIT | Not Critical | 73
Not Started | Req Fire Rough In | Auscoast Fire | [6 empty] | 2024-10-31 |  | 2024-10-31 |  | 1d | WATER TANKS | Not Critical | 73
Not Started | Req Carpenter Soffits Ground Floor | Tekna Carpentry | [6 empty] | 2024-11-01 |  | 2024-11-04 |  | 2d | CARPENTER | Not Critical | 73, 89
Not Started | Req Install Ply to Bathrooms | Tekna Carpentry | [6 empty] | 2024-11-05 |  | 2024-11-05 |  | 1d | CARPENTER | Not Critical | 88
Not Started | Do Plumbing Rough-In Inspection | Plumber | [6 empty] | 2024-11-05 |  | 2024-11-05 |  | 1d | PLUMBER | Not Critical | 88
Not Started | Req Carpenter Cladding | Tekna Carpentry | [6 empty] | 2024-11-05 |  | 2024-11-11 |  | 5d | CARPENTER | Critical | 91
Not Started | Do Inspection NDIS - Frame | Andrew Clement | [6 empty] | 2024-11-06 |  | 2024-11-06 |  | 1d | NDIS | Critical | 92
Not Started | PHOTO - Ply Bathrooms, Bedroom Crane Supports | Andrew Clement | [6 empty] | 2024-11-06 |  | 2024-11-06 |  | 1d | SUPERVISOR | Not Critical | 92
Not Started | CERTIFICATE - 08 Compliance Certificate - Glazing - Window and Doors | Sophie Harder | [6 empty] | 2024-11-06 |  | 2024-11-06 |  | 1d | ADMIN | Not Critical | 76FS +5d
Not Started | PHOTO - Enclosed | Andrew Clement | [6 empty] | 2024-11-12 |  | 2024-11-12 |  | 1d | SUPERVISOR | Not Critical | 94
Not Started | Req Down Pipes Ground Floor | Plumber | [6 empty] | 2024-11-12 |  | 2024-11-12 |  | 1d | PLUMBER | Not Critical | 94
Not Started | CLAIM - Enclosed | Sophie Harder | [6 empty] | 2024-11-13 |  | 2024-11-19 |  | 5d | ADMIN | Critical | 94, 98
Not Started | CERTIFICATE - 03 Form 12 Engineering Slab | Sophie Harder | [6 empty] | 2024-10-28 |  | 2024-10-28 |  | 1d | ADMIN | Not Critical | 38FS +10d
Not Started | FIXING | [7 empty] | 2024-11-05 |  | 2024-12-23 |  | 35d |  | Not Critical
Not Started | Req Ceiling & Wall Insulation Before Plasterboard | Austral Insulation | [6 empty] | 2024-11-05 |  | 2024-11-05 |  | 1d | INSULATION | Not Critical | 88, 87, 90, 86, 85
Not Started | Req Plaster Board | DAMS Plasterboard | [6 empty] | 2024-11-06 |  | 2024-11-14 |  | 7d | PLASTER BOARD | Critical | 93, 86, 87, 88, 103
Not Started | Req Internal Fixout | Prehung Doors | [6 empty] | 2024-11-14 |  | 2024-11-14 |  | 1d | FIX-OUT MATERIALS | Not Critical | 107SS -1d
Not Started | Req Site Clean After Plasterboard & Brickwork | Tekna Site | [6 empty] | 2024-11-15 |  | 2024-11-15 |  | 1d |  |  | 104, 94
Not Started | Req Carpenter Fixout | Tekna Carpentry | [6 empty] | 2024-11-15 |  | 2024-11-18 |  | 2d | CARPENTER | Not Critical | 104
Not Started | Req Garage Doors | Sunstate Garage Doors | [6 empty] | 2024-11-15 |  | 2024-11-15 |  | 1d | GARAGE DOORS | Critical | 104
Not Started | SPO - Electrician - Cutouts | Electrican | [6 empty] | 2024-11-15 |  | 2024-11-15 |  | 1d | ELECTRICAL | Not Critical | 104
Not Started | Req Internal Door Handles | Prehung Doors | [6 empty] | 2024-11-15 |  | 2024-11-15 |  | 1d | FIX-OUT MATERIALS | Not Critical | 107SS
Not Started | FIT - Auto Door Openers | Tekna Finishing Touches | [6 empty] | 2024-11-19 |  | 2024-11-20 |  | 2d | CARPENTER | Not Critical | 107
Not Started | Req Kitchen | Tekna Kitchens | [6 empty] | 2024-11-19 |  | 2024-11-25 |  | 5d | KITCHEN | Critical | 107
Not Started | Req Water Proofer | Wayke Waterproofing | [6 empty] | 2024-11-19 |  | 2024-11-20 |  | 2d | WATER PROOFER | Not Critical | 107
Not Started | Req Tiles | National Tiles CO PTY LTD | [6 empty] | 2024-11-25 |  | 2024-11-25 |  | 1d | TILE | Not Critical | 116SS -1d
Not Started | Do Make and Install Kitchen | Tekna Kitchens | [6 empty] | 2024-11-26 |  | 2024-12-02 |  | 5d |  |  | 112 | 100%
Not Started | Req Tiler | Joii Tiling | [6 empty] | 2024-11-26 |  | 2024-12-04 |  | 7d | TILER | Not Critical | 112, 113
Not Started | SPO - Plaster Fit Cornice | DAMS Plasterboard | [6 empty] | 2024-11-26 |  | 2024-11-26 |  | 1d | PLASTER BOARD | Not Critical | 112
Not Started | CERTIFICATE - 11 Form 43 - Waterproofing | Sophie Harder | [6 empty] | 2024-11-28 |  | 2024-11-28 |  | 1d | ADMIN | Not Critical | 113FS +5d
Not Started | Req Painter Internal House | Painter | [6 empty] | 2024-12-05 |  | 2024-12-13 |  | 7d | PAINTER | Critical | 116
Not Started | Measure Shower Screens Book Fitting | Civic Shower Screens & Wardrobes | [6 empty] | 2024-12-05 |  | 2024-12-05 |  | 1d | SHOWER SCREENS | Not Critical | 116
Not Started | Req Pre Paint (Including Sanding) | DAMS Plasterboard | [6 empty] | 2024-12-06 |  | 2024-12-09 |  | 2d | PLASTER BOARD | Not Critical | 119SS +1d
Not Started | PHOTO - Fixing | Andrew Clement | [6 empty] | 2024-12-16 |  | 2024-12-16 |  | 1d | SUPERVISOR | Not Critical | 114, 119
Not Started | Req Painter External House | Painter | [6 empty] | 2024-12-16 |  | 2024-12-17 |  | 2d | PAINTER | Not Critical | 119, 94, 99
Not Started | CLAIM - Fixing | Sophie Harder | [6 empty] | 2024-12-17 |  | 2024-12-23 |  | 5d | ADMIN | Critical | 116, 119, 122
Not Started | DRIVEWAY | [7 empty] | 2024-12-03 |  | 2024-12-06 |  | 4d |  | Not Critical
Not Started | Req Driveway Kerb Cut Out | [7 empty] | 2024-12-03 |  | 2024-12-03 |  | 1d | DRIVEWAY | Not Critical | 129SS -2d
Not Started | FIT - Drains to Front of Doors | Tekna Finishing Touches | [6 empty] | 2024-12-03 |  | 2024-12-03 |  | 1d | CARPENTER | Not Critical | 129SS -2d
Not Started | Req Driveway Steel Reo | Mesh and Bar | [6 empty] | 2024-12-04 |  | 2024-12-04 |  | 1d | DRIVEWAY | Not Critical | 129SS -1d
Not Started | Req Driveway Concretor | Opel Concrete Pty Ltd | [6 empty] | 2024-12-05 |  | 2024-12-05 |  | 1d | DRIVEWAY | Critical | 99, 116
Not Started | PHOTO - Driveway | Andrew Clement | [6 empty] | 2024-12-06 |  | 2024-12-06 |  | 1d | SUPERVISOR | Not Critical | 129
Not Started | Req Driveway Prep Site Clean | Tekna Site | [10 empty] | 1d
Not Started | LANDSCAPING | [7 empty] | 2024-12-06 |  | 2024-12-17 |  | 8d |  | Not Critical
Not Started | Req Retaining Wall | Joii Landscaping | [6 empty] | 2024-12-06 |  | 2024-12-09 |  | 2d | RETAINING WALL | Not Critical | 129
Not Started | Req Fence | Joii Landscaping | [6 empty] | 2024-12-10 |  | 2024-12-11 |  | 2d | FENCING | Not Critical | 133, 129
Not Started | Req Landscaping | Joii Landscaping | [6 empty] | 2024-12-12 |  | 2024-12-16 |  | 3d | LANDSCAPING | Critical | 134
Not Started | PHOTO - Fence and Landscaping | Andrew Clement | [6 empty] | 2024-12-17 |  | 2024-12-17 |  | 1d | SUPERVISOR | Not Critical | 134, 135
Not Started | Req Landscape Prep Final Site Clean | Tekna Site | [10 empty] | 1d
Not Started | PRACTICAL COMPLETION | [7 empty] | 2024-12-13 |  | 2025-01-02 |  | 15d |  | Not Critical
Not Started | Req Hot Water System | Chromagen Australia Pty Ltd | [6 empty] | 2024-12-13 |  | 2024-12-13 |  | 1d | PLUMBING FITOFF GEAR | Not Critical | 146SS -1d
Not Started | Req Plumber Fitoff Gear | Harvey Norman Commerical - Plumbing | [6 empty] | 2024-12-13 |  | 2024-12-13 |  | 1d | PLUMBING FITOFF GEAR | Not Critical | 146SS -1d
Not Started | Req Fire System Fitoff | Auscoast Fire | [6 empty] | 2024-12-16 |  | 2024-12-16 |  | 1d | FIRE | Critical | 119, 116
Not Started | Req Electrical Items | Harvey Norman Commerical - Appliance | [6 empty] | 2024-12-16 |  | 2024-12-16 |  | 1d | ELECTRICAL ITEMS | Not Critical | 151SS -1d
Not Started | Req Vinyl Sliders | Civic Shower Screens & Wardrobes | [6 empty] | 2024-12-16 |  | 2024-12-16 |  | 1d | SHOWER SCREENS | Not Critical | 119, 116
Not Started | Req Window Coverings | Lovering Installations QLD | [6 empty] | 2024-12-16 |  | 2024-12-16 |  | 1d | TURN KEY | Not Critical | 119, 116
Not Started | Req Carpenter For Final Fitoff | Tekna Carpentry | [6 empty] | 2024-12-16 |  | 2024-12-16 |  | 1d | CARPENTER | Not Critical | 116, 119
Not Started | Req Plumber - Fit Off | Plumber | [6 empty] | 2024-12-16 |  | 2024-12-17 |  | 2d | PLUMBER | Critical | 116, 119
Not Started | Req Shower Screens | Civic Shower Screens & Wardrobes | [6 empty] | 2024-12-16 |  | 2024-12-16 |  | 1d | SHOWER SCREENS | Not Critical | 116, 119
Not Started | Req SAT System | Stratus | [6 empty] | 2024-12-16 |  | 2024-12-16 |  | 1d | ELECTRICAL ITEMS | Not Critical | 151SS -1d
Not Started | CERTIFICATE - 09 Form 15 - Shower Screens | Sophie Harder | [6 empty] | 2024-12-17 |  | 2024-12-17 |  | 1d | ADMIN | Not Critical | 147
Not Started | Do Finishing Touches | Andrew Clement | [6 empty] | 2024-12-17 |  | 2024-12-23 |  | 5d | SUPERVISOR | Not Critical | 145
Not Started | Req Electrician - Fit Off | Electrican | [6 empty] | 2024-12-17 |  | 2024-12-19 |  | 3d | ELECTRICAL | Critical | 116, 119, 144
Not Started | DO - Courtyard Seat and Sprinkler | Tekna Finishing Touches | [6 empty] | 2024-12-17 |  | 2024-12-17 |  | 1d | CARPENTER | Not Critical | 145
Not Started | Do Plumbing Final Inspection | Plumber | [6 empty] | 2024-12-18 |  | 2024-12-18 |  | 1d | PLUMBER | Not Critical | 146
Not Started | Req Gapping To Skirting and Expansion Joints | A1 Builders Finals/Services Group | [6 empty] | 2024-12-18 |  | 2024-12-18 |  | 1d | FINISHING TOUCHES | Not Critical | 146, 145
Not Started | Req Air Conditioning Fit Off | Star Airconditioning | [6 empty] | 2024-12-18 |  | 2024-12-18 |  | 1d | AIR CONDITIONING | Not Critical | 151FF -1d
Not Started | GET - All Forms for Final Inspection | Sophie Harder | [6 empty] | 2024-12-18 |  | 2024-12-18 |  | 1d | ADMIN | Not Critical | 171SS -5d
Not Started | DO - Get Hot Water Rebate | Sophie Harder | [6 empty] | 2024-12-19 |  | 2024-12-19 |  | 1d | ADMIN | Not Critical | 153
Not Started | Req Site Clean Final | Tekna Site | [6 empty] | 2024-12-20 |  | 2024-12-20 |  | 1d |  |  | 146, 151
Not Started | Req Full Turn Key Package | Lovering Installations QLD | [6 empty] | 2024-12-20 |  | 2024-12-20 |  | 1d | TURN KEY | Not Critical | 151, 146
Not Started | Req Painter Touch Ups | Painter | [6 empty] | 2024-12-20 |  | 2024-12-20 |  | 1d | PAINTER | Not Critical | 146, 151, 143
Not Started | Req Solar Panel Commisions | Open Electrical | [6 empty] | 2024-12-20 |  | 2024-12-20 |  | 1d | SOLAR | Not Critical | 151
Not Started | CERTIFICATE - 10 Form 12 - Smoke Alarms | Sophie Harder | [6 empty] | 2024-12-20 |  | 2024-12-20 |  | 1d | ADMIN | Not Critical | 151
Not Started | Req Ceiling Insulation | Austral Insulation | [6 empty] | 2024-12-23 |  | 2024-12-23 |  | 1d | INSULATION | Not Critical | 151, 161
Not Started | Req Vinyl Floor | Joii Flooring | [6 empty] | 2024-12-23 |  | 2024-12-23 |  | 1d | FLOOR COVERINGS | Critical | 159
Not Started | Req Window Handover Service | Southern Star Windows | [6 empty] | 2024-12-23 |  | 2024-12-23 |  | 1d | WINDOWS | Not Critical | 159
Not Started | SPO - Insulation Spread Ceiling Insulation | Austral Insulation | [6 empty] | 2024-12-23 |  | 2024-12-23 |  | 1d | INSULATION | Not Critical | 151, 161
Not Started | Do - Put Termite Sticker In MeterBox and Kitchen Cupboard | Andrew Clement | [6 empty] | 2024-12-24 |  | 2024-12-24 |  | 1d | SUPERVISOR | Not Critical | 171SS -1d
Not Started | Req Builders Clean | A1 Builders Finals/Services Group | [6 empty] | 2024-12-24 |  | 2024-12-24 |  | 1d | HOUSE CLEAN | Not Critical | 151, 161, 164, 150
Not Started | CERTIFICATE - 06 Form 43 Energy Efficiency | Sophie Harder | [6 empty] | 2024-12-24 |  | 2024-12-24 |  | 1d | ADMIN | Not Critical | 163
Not Started | PHOTO - Practical Completion | Andrew Clement | [6 empty] | 2024-12-25 |  | 2024-12-25 |  | 1d | SUPERVISOR | Not Critical | 168
Not Started | Do Council Final Inspection | Andrew Clement | [6 empty] | 2024-12-25 |  | 2024-12-25 |  | 1d | PRIVATE CERTIFIER | Critical | 168
Not Started | GET - Form 11/21 from Certifier | Sophie Harder | [6 empty] | 2024-12-26 |  | 2024-12-26 |  | 1d | ADMIN | Not Critical | 171
Not Started | CREATE - Builder Confirmation | Sophie Harder | [6 empty] | 2024-12-26 |  | 2024-12-26 |  | 1d | ADMIN | Not Critical | 171
Started | GET - Engineer For Future Ceiling | Sophie Harder |  |  |  | TRUE |  |  | 2024-12-26 | 2024-08-30 | 2024-12-26 |  | 1d | ADMIN | Not Critical
Not Started | GET - SDA Site Density Report | Sophie Harder | [6 empty] | 2024-12-26 |  | 2024-12-26 |  | 1d | ADMIN | Not Critical | 171
Not Started | CREATE - Evacuation Plan | Sophie Harder | [6 empty] | 2024-12-26 |  | 2024-12-26 |  | 1d | ADMIN | Not Critical | 171
Not Started | CLAIM - Practical Completion | Sophie Harder | [6 empty] | 2024-12-26 |  | 2025-01-01 |  | 5d | ADMIN | Critical | 171
Not Started | DO - NDIS Final Inspection | Access Allways | [6 empty] | 2024-12-27 |  | 2024-12-27 |  | 1d | NDIS | Critical | 171, 173, 176
Not Started | DO - Final Payment has been made, Organize Handover house | Andrew Clement | [6 empty] | 2025-01-02 |  | 2025-01-02 |  | 1d | SUPERVISOR | Not Critical | 171, 177

## Comments
Row 178 | We require the following evidence prior to attending site: • Form 11/21 from Building Certifier (Final Certification) • SDA Provider - Site density of SDA Complies with density requirements • Architect – Site Plan (including common areas) and Final Internal Floor Plan • Builder/Architect/Fire Engineer – Emergency Evacuation Plan (also must be displayed in each dwelling at time of final inspection) • Builder – letter confirmation in regard to the provision of: • Slip resistance to all areas (applies to all areas). Applies to all design categories • Reinforcement of 12mm thick, extending to height of 2100mm or concrete/masonry walls. Applies to all design categories • Carpet pile height or thickness of not more than 11mm and backing not more than 4mm. Applies to all design categories • Where ducted air-conditioning is provided, zoning of habitable rooms is provided. Applies to FA and HPS • Internet connection has been provided throughout the house. Applies to FA and HPS • Qualified, Insured and Practising Structural Engineer – letter that states that the participants bedroom has been inspected and have been provided with power and inbuilt structure capable of installation of a minimum 250kg load capacity, constant charge ceiling hoist which is capable of going across the bed and down the bed. Applies to HPS We require the above evidence at least 2 days prior to us attending site. Should you have any questions, please do not hesitate to contact. | Robert Harder | 09/07/24 6:41 AM