## UpHomes NDIS Template
title | Status | Start | Complete | duration | supplier_category | Supplier | Paid Internal | Approx Date | confirm | supplier_confirm | Task Started | Completed | Predecessors | Attachements
CREATE - Contract | Not Started | 2024-07-16 | 2024-07-16 | 1d | ADMIN | Sophie Harder
DO - Load Invoices into XERO | Not Started | 2024-07-17 | 2024-07-17 | 1d | ADMIN | Sophie Harder | [6 empty] | 1
GET - Finance Approval | Not Started | 2024-07-17 | 2024-08-14 | 21d | ADMIN | Sophie Harder | [6 empty] | 1
CLAIM - DEPOSIT |  | 2024-08-15 | 2024-08-21 | 5d | ADMIN | Sophie Harder | [6 empty] | 3
ORDER - Soil Test and Wind Rating & Slab Design | Not Started | 2024-08-22 | 2024-08-28 | 5d | ADMIN | Sophie Harder | [6 empty] | 4
ORDER - Contour Survey Plan | Not Started | 2024-08-22 | 2024-08-28 | 5d | ADMIN | Sophie Harder | [6 empty] | 4
DO - Working Drawings | Not Started | 2024-08-29 | 2024-08-29 | 1d | ADMIN | Sophie Harder | [6 empty] | 4, 6
DO - Plumbing Approval | Not Started | 2024-08-22 | 2024-08-22 | 1d | ADMIN | Sophie Harder | [6 empty] | 3, 4
DO - QLeave | Not Started | 2024-08-22 | 2024-08-22 | 1d | ADMIN | Sophie Harder | [6 empty] | 3, 4
DO - Hydraulics Design | Not Started | 2024-08-22 | 2024-08-22 | 1d | ADMIN | Sophie Harder | [6 empty] | 3, 4
DO - Energy Efficiency | Not Started | 2024-08-22 | 2024-08-22 | 1d | ADMIN | Sophie Harder | [6 empty] | 3, 4
CHECK - Land Settlement | Not Started | 2024-08-22 | 2024-08-22 | 1d | ADMIN | Sophie Harder | [6 empty] | 3, 4
DO - Covenant Approval (if required) | Not Started | 2024-08-30 | 2024-08-30 | 1d | ADMIN | Sophie Harder | [6 empty] | 7
DO - Certification | Not Started | 2024-08-23 | 2024-09-05 | 10d | ADMIN | Sophie Harder | [6 empty] | 8, 9, 10, 11
DO - Driveway Application | Not Started | 2024-09-06 | 2024-09-06 | 1d | ADMIN | Sophie Harder | [6 empty] | 14
ORDER - Trusses | Not Started | 2024-09-06 | 2024-09-06 | 1d | ADMIN | Sam Harder | [6 empty] | 12, 14
ORDER - Window Actuators | Not Started | 2024-09-06 | 2024-09-06 | 1d | ADMIN | Sam Harder | [6 empty] | 12, 14
ORDER - Kitchen Parts | Not Started | 2024-09-06 | 2024-09-06 | 1d | ADMIN | Sam Harder | [6 empty] | 12, 14
ORDER - Door Automation | Not Started | 2024-09-06 | 2024-09-06 | 1d | ADMIN | Sam Harder | [6 empty] | 12, 14
ORDER - Plumbing Items | Not Started | 2024-09-06 | 2024-09-06 | 1d | ADMIN | Sam Harder | [6 empty] | 12, 14
ORDER - Frame | Not Started | 2024-09-06 | 2024-09-06 | 1d | ADMIN | Sam Harder | [6 empty] | 12, 14
ORDER - Roof | Not Started | 2024-09-06 | 2024-09-06 | 1d | ADMIN | Sam Harder | [6 empty] | 12, 14
ORDER - EXT Doors | Not Started | 2024-09-06 | 2024-09-06 | 1d | ADMIN | Sam Harder | [6 empty] | 12, 14
ORDER - Surveyor | Not Started | 2024-09-06 | 2024-09-06 | 1d | ADMIN | Sam Harder | [6 empty] | 12, 14
ORDER - Windows | Not Started | 2024-09-06 | 2024-09-06 | 1d | ADMIN | Sam Harder | [6 empty] | 12, 14
Req Site Cut | Not Started | 2024-09-06 | 2024-09-06 | 1d | SITE WORKS | Andrew Clement | [6 empty] | 12, 14
SLAB | Not Started | 2024-09-09 | 2024-09-30 | 16d
Req Surveyor to Setout Wafflepod | Not Started | 2024-09-09 | 2024-09-09 | 1d | SURVEYOR | Survey Mark | [6 empty] | 26
Req Drainer for Drains Wafflepod | Not Started | 2024-09-10 | 2024-09-11 | 2d | PLUMBER | Plumber | [6 empty] | 28
Req Electrician Underground (INC NBN) | Not Started | 2024-09-10 | 2024-09-10 | 1d | ELECTRICAL | Electrican | [6 empty] | 29SS
Req Power To Site | Not Started | 2024-09-11 | 2024-09-24 | 10d | ADMIN | Sophie Harder | [6 empty] | 30
Req Concreter For Complete Slab Labour And Materials | Not Started | 2024-09-12 | 2024-09-13 | 2d | CONCRETOR | JND Concrete | [6 empty] | 28, 29, 30
Req Termite Protection Penetrations | Not Started | 2024-09-12 | 2024-09-12 | 1d | TERMITE PROTECTION | Bittn Australia PTY Ltd | [6 empty] | 32SS
PHOTO - Slab | Not Started | 2024-09-16 | 2024-09-16 | 1d | SUPERVISOR | Andrew Clement | [6 empty] | 32
Req Waterproof Slab Edge | Not Started | 2024-09-16 | 2024-09-16 | 1d | SUPERVISOR | Andrew Clement | [6 empty] | 32
CLAIM - Slab | Not Started | 2024-09-16 | 2024-09-20 | 5d | ADMIN | Sophie Harder | [6 empty] | 32
CERTIFICATE - Surveyor | Not Started | 2024-09-24 | 2024-09-24 | 1d | ADMIN | Sophie Harder | [6 empty] | 28FS +10d
CERTIFICATE - Engineer Slab | Not Started | 2024-09-30 | 2024-09-30 | 1d | ADMIN | Sophie Harder | [6 empty] | 32FS +10d
FRAME | Not Started | 2024-09-17 | 2024-10-02 | 12d
Req Frame Hardware | Not Started | 2024-09-17 | 2024-09-17 | 1d | TIMBER FRAME | Bunnings | [6 empty] | 42SS -1d
Req Frame Material Ground Floor | Not Started | 2024-09-17 | 2024-09-17 | 1d | TIMBER FRAME | Bunnings | [6 empty] | 42SS -1d
Req Carpenter Ground Floor | Not Started | 2024-09-18 | 2024-09-24 | 5d | CARPENTER | Tekna Carpentry | [6 empty] | 32FS +2d
Req Termite Perimeter | Not Started | 2024-09-18 | 2024-09-18 | 1d | TERMITE PROTECTION | Bittn Australia PTY Ltd | [6 empty] | 42SS
Req Roof Trusses | Not Started | 2024-09-20 | 2024-09-20 | 1d | TRUSSES | Bunnings | [6 empty] | 42SS +2d | Req Floor Plan
Req Crane Roof Trusses | Not Started | 2024-09-20 | 2024-09-20 | 1d | CRANE | Crane | [6 empty] | 44SS
Req Steel Posts | Not Started | 2024-09-23 | 2024-09-23 | 1d | STEEL BEAMS/POSTS | Harveys Towing | [6 empty] | 44 | Req Engineer Drawings and floor plan
PHOTO - Frame | Not Started | 2024-09-25 | 2024-09-25 | 1d | SUPERVISOR | Andrew Clement | [6 empty] | 42
Do Frame Inspection | Not Started | 2024-09-25 | 2024-09-25 | 1d | ENGINEER | Andrew Clement | [6 empty] | 42
Req Partition Wall | Not Started | 2024-09-25 | 2024-09-25 | 1d | PARTITION WALL | [7 empty] | 42
CERTIFICATE - Engineer Frame INC Hoist | Not Started | 2024-09-26 | 2024-09-26 | 1d | ADMIN | Sophie Harder | [6 empty] | 48
CERTIFICATE - Termite | Not Started | 2024-09-26 | 2024-09-26 | 1d | ADMIN | Sophie Harder | [6 empty] | 43FS +5d
CLAIM - Frame | Not Started | 2024-09-26 | 2024-10-02 | 5d | ADMIN | Sophie Harder | [6 empty] | 42, 47
CERTIFICATE - Roof Trusses | Not Started | 2024-09-30 | 2024-09-30 | 1d | ADMIN | Sophie Harder | [6 empty] | 44FS +5d
ENCLOSED | Not Started | 2024-09-26 | 2024-10-22 | 19d
Req Fascia and Gutter and Colorbond Roof | Not Started | 2024-09-26 | 2024-10-02 | 5d | ROOF | Joii Roofing | [6 empty] | 42, 49
Req External Doors | Not Started | 2024-10-01 | 2024-10-01 | 1d | ENT DOORS | Prehung Doors | [6 empty] | 55FF -1d
Req Windows | Not Started | 2024-10-01 | 2024-10-01 | 1d | WINDOWS | Southern Star Windows | [6 empty] | 55FF -1d
Req External Door Handle Locks | Not Started | 2024-10-01 | 2024-10-01 | 1d | ENT DOORS | Prehung Doors | [6 empty] | 56SS
Req Carpenter Install Windows/Doors | Not Started | 2024-10-02 | 2024-10-02 | 1d | CARPENTER | Tekna Carpentry | [6 empty] | 42, 49, 57
Req Carpenter Straighten Frame | Not Started | 2024-10-02 | 2024-10-02 | 1d | CARPENTER | Tekna Carpentry | [6 empty] | 59SS
Req Mixer Bodies For Plumber Rough In | Not Started | 2024-10-02 | 2024-10-02 | 1d | PLUMBING FITOFF GEAR | Harvey Norman Commerical - Plumbing | [6 empty] | 68SS -1d
FIT - Window Actuators | Not Started | 2024-10-02 | 2024-10-02 | 1d | CARPENTER | Tekna Carpentry | [6 empty] | 57, 59SS
Req Wall Sisilation Ground Floor | Not Started | 2024-10-02 | 2024-10-02 | 1d | INSULATION | Austral Insulation | [6 empty] | 59SS
Req Measure Garage Doors | Not Started | 2024-10-03 | 2024-10-03 | 1d | GARAGE DOORS | Sunstate Garage Doors | [6 empty] | 59
Req Rough In Solar Panels | Not Started | 2024-10-03 | 2024-10-03 | 1d | SOLAR | Open Electrical | [6 empty] | 55
Req Air Conditioning Rough In | Not Started | 2024-10-03 | 2024-10-03 | 1d | AIR CONDITIONING | Star Airconditioning | [6 empty] | 55
Req Electrician - Prewire | Not Started | 2024-10-03 | 2024-10-07 | 3d | ELECTRICAL | Electrican | [6 empty] | 55
Req Plumber Rough In | Not Started | 2024-10-03 | 2024-10-07 | 3d | PLUMBER | Plumber | [6 empty] | 55
Req Soffit Hardware and Cladding | Not Started | 2024-10-03 | 2024-10-03 | 1d | SOFFIT | Bunnings | [6 empty] | 55
Req Fire Rough In | Not Started | 2024-10-03 | 2024-10-03 | 1d | WATER TANKS | Auscoast Fire | [6 empty] | 55
Req Carpenter Soffits Ground Floor | Not Started | 2024-10-04 | 2024-10-07 | 2d | CARPENTER | Tekna Carpentry | [6 empty] | 55, 69
Req Install Ply to Bathrooms | Not Started | 2024-10-08 | 2024-10-08 | 1d | CARPENTER | Tekna Carpentry | [6 empty] | 68
Do Plumbing Rough-In Inspection | Not Started | 2024-10-08 | 2024-10-08 | 1d | PLUMBER | Plumber | [6 empty] | 68
Req Carpenter Cladding | Not Started | 2024-10-08 | 2024-10-14 | 5d | CARPENTER | Tekna Carpentry | [6 empty] | 71
Do Inspection NDIS |  | 2024-10-09 | 2024-10-09 | 1d | NDIS | Andrew Clement | [6 empty] | 72
PHOTO - Ply Bathrooms, Bedroom Crane Supports | Not Started | 2024-10-09 | 2024-10-09 | 1d | SUPERVISOR | Andrew Clement | [6 empty] | 72
CERTIFICATE - Windows | Not Started | 2024-10-09 | 2024-10-09 | 1d | ADMIN | Sophie Harder | [6 empty] | 57FS +5d
PHOTO - Enclosed | Not Started | 2024-10-15 | 2024-10-15 | 1d | SUPERVISOR | Andrew Clement | [6 empty] | 74
Req Down Pipes Ground Floor | Not Started | 2024-10-15 | 2024-10-15 | 1d | PLUMBER | Plumber | [6 empty] | 74
CLAIM - Enclosed | Not Started | 2024-10-16 | 2024-10-22 | 5d | ADMIN | Sophie Harder | [6 empty] | 74, 78
FIXING | Not Started | 2024-10-08 | 2024-11-25 | 35d
Req Ceiling & Wall Insulation Before Plasterboard | Not Started | 2024-10-08 | 2024-10-08 | 1d | INSULATION | Austral Insulation | [6 empty] | 68, 67, 70, 66, 65
Req Plaster Board | Not Started | 2024-10-09 | 2024-10-17 | 7d | PLASTER BOARD | DAMS Plasterboard | [6 empty] | 73, 66, 67, 68, 82
Req Internal Fixout | Not Started | 2024-10-17 | 2024-10-17 | 1d | FIX-OUT MATERIALS | Prehung Doors | [6 empty] | 85SS -1d
Req Carpenter Fixout | Not Started | 2024-10-18 | 2024-10-21 | 2d | CARPENTER | Tekna Carpentry | [6 empty] | 83
Req Garage Doors | Not Started | 2024-10-18 | 2024-10-18 | 1d | GARAGE DOORS | Sunstate Garage Doors | [6 empty] | 83
SPO - Electrician - Cutouts | Not Started | 2024-10-18 | 2024-10-18 | 1d | ELECTRICAL | Electrican | [6 empty] | 83
Req Internal Door Handles | Not Started | 2024-10-18 | 2024-10-18 | 1d | FIX-OUT MATERIALS | Prehung Doors | [6 empty] | 85SS
FIT - Auto Door Openers | Not Started | 2024-10-22 | 2024-10-23 | 2d | CARPENTER | Tekna Carpentry | [6 empty] | 85
Req Kitchen | Not Started | 2024-10-22 | 2024-10-28 | 5d | KITCHEN | Tekna Kitchens | [6 empty] | 85
Req Water Proofer | Not Started | 2024-10-22 | 2024-10-23 | 2d | WATER PROOFER | Wayke Waterproofing | [6 empty] | 85
Req Tiles | Not Started | 2024-10-28 | 2024-10-28 | 1d | TILE | National Tiles CO PTY LTD | [6 empty] | 93SS -1d
Req Tiler | Not Started | 2024-10-29 | 2024-11-06 | 7d | TILER | Joii Tiling | [6 empty] | 90, 91
SPO - Plaster Fit Cornice | Not Started | 2024-10-29 | 2024-10-29 | 1d | PLASTER BOARD | DAMS Plasterboard | [6 empty] | 90
CERTIFICATE - Waterproofer | Not Started | 2024-10-31 | 2024-10-31 | 1d | ADMIN | Sophie Harder | [6 empty] | 91FS +5d
Req Painter Internal House | Not Started | 2024-11-07 | 2024-11-15 | 7d | PAINTER | Painter | [6 empty] | 93
Measure Shower Screens Book Fitting | Not Started | 2024-11-07 | 2024-11-07 | 1d | SHOWER SCREENS | Civic Shower Screens & Wardrobes | [6 empty] | 93
Req Pre Paint (Including Sanding) | Not Started | 2024-11-08 | 2024-11-11 | 2d | PLASTER BOARD | DAMS Plasterboard | [6 empty] | 96SS +1d
PHOTO - Fixing | Not Started | 2024-11-18 | 2024-11-18 | 1d | SUPERVISOR | Andrew Clement | [6 empty] | 92, 96
Req Painter External House | Not Started | 2024-11-18 | 2024-11-19 | 2d | PAINTER | Painter | [6 empty] | 96, 74, 79
CLAIM - Fixing | Not Started | 2024-11-19 | 2024-11-25 | 5d | ADMIN | Sophie Harder | [6 empty] | 93, 96, 99
DRIVEWAY | Not Started | 2024-11-05 | 2024-11-08 | 4d
Req Driveway Kerb Cut Out | Not Started | 2024-11-05 | 2024-11-05 | 1d | DRIVEWAY | [7 empty] | 106SS -2d
FIT - Drains to Front of Doors | Not Started | 2024-11-05 | 2024-11-05 | 1d | SUPERVISOR | Tekna Carpentry | [6 empty] | 106SS -2d
Req Driveway Steel Reo | Not Started | 2024-11-06 | 2024-11-06 | 1d | DRIVEWAY | Mesh and Bar | [6 empty] | 106SS -1d
Req Driveway Concretor | Not Started | 2024-11-07 | 2024-11-07 | 1d | DRIVEWAY | Opel Concrete Pty Ltd | [6 empty] | 79, 93
PHOTO - Driveway | Not Started | 2024-11-08 | 2024-11-08 | 1d | SUPERVISOR | Andrew Clement | [6 empty] | 106
LANDSCAPING | Not Started | 2024-11-08 | 2024-11-19 | 8d
Req Retaining Wall | Not Started | 2024-11-08 | 2024-11-11 | 2d | RETAINING WALL | Joii Landscaping | [6 empty] | 106
Req Fence | Not Started | 2024-11-12 | 2024-11-13 | 2d | FENCING | Joii Landscaping | [6 empty] | 109, 106
Req Landscaping | Not Started | 2024-11-14 | 2024-11-18 | 3d | LANDSCAPING | Joii Landscaping | [6 empty] | 110
PHOTO - Fence and Landscaping | Not Started | 2024-11-19 | 2024-11-19 | 1d | SUPERVISOR | Andrew Clement | [6 empty] | 110, 111
PRACTICAL COMPLETION | Not Started | 2024-11-15 | 2024-12-05 | 15d
Req Hot Water System | Not Started | 2024-11-15 | 2024-11-15 | 1d | PLUMBING FITOFF GEAR | Chromagen Australia Pty Ltd | [6 empty] | 121SS -1d
Req Plumber Fitoff Gear | Not Started | 2024-11-15 | 2024-11-15 | 1d | PLUMBING FITOFF GEAR | Harvey Norman Commerical - Plumbing | [6 empty] | 121SS -1d
Req Fire System Fitoff | Not Started | 2024-11-18 | 2024-11-18 | 1d | FIRE | Auscoast Fire | [6 empty] | 96, 93
Req Electrical Items | Not Started | 2024-11-18 | 2024-11-18 | 1d | ELECTRICAL ITEMS | Harvey Norman Commerical - Appliance | [6 empty] | 127SS -1d
Req Vinyl Sliders | Not Started | 2024-11-18 | 2024-11-18 | 1d | SHOWER SCREENS | Civic Shower Screens & Wardrobes | [6 empty] | 96, 93
Req Window Coverings | Not Started | 2024-11-18 | 2024-11-18 | 1d | TURN KEY | Lovering Installations QLD | [6 empty] | 96, 93
Req Carpenter For Final Fitoff | Not Started | 2024-11-18 | 2024-11-18 | 1d | CARPENTER | Tekna Carpentry | [6 empty] | 93, 96
Req Plumber - Fit Off | Not Started | 2024-11-18 | 2024-11-19 | 2d | PLUMBER | Plumber | [6 empty] | 93, 96
Req Shower Screens | Not Started | 2024-11-18 | 2024-11-18 | 1d | SHOWER SCREENS | Civic Shower Screens & Wardrobes | [6 empty] | 93, 96
Req SAT System | Not Started | 2024-11-18 | 2024-11-18 | 1d | ELECTRICAL ITEMS | Stratus | [6 empty] | 127SS -1d
CERTIFICATE - Fire Alarms | Not Started | 2024-11-19 | 2024-11-19 | 1d | ADMIN | Sophie Harder | [6 empty] | 116
CERTIFICATE - Shower Screens | Not Started | 2024-11-19 | 2024-11-19 | 1d | ADMIN | Sophie Harder | [6 empty] | 122
Do Finishing Touches | Not Started | 2024-11-19 | 2024-11-25 | 5d | SUPERVISOR | Andrew Clement | [6 empty] | 120
Req Electrician - Fit Off | Not Started | 2024-11-19 | 2024-11-21 | 3d | ELECTRICAL | Electrican | [6 empty] | 93, 96, 119
Do Plumbing Final Inspection | Not Started | 2024-11-20 | 2024-11-20 | 1d | PLUMBER | Plumber | [6 empty] | 121
Req Gapping To Skirting and Expansion Joints | Not Started | 2024-11-20 | 2024-11-20 | 1d | FINISHING TOUCHES | A1 Builders Finals/Services Group | [6 empty] | 121, 120
Req Air Conditioning Fit Off | Not Started | 2024-11-20 | 2024-11-20 | 1d | AIR CONDITIONING | Star Airconditioning | [6 empty] | 127FF -1d
GET - All Forms for Final Inspection | Not Started | 2024-11-20 | 2024-11-20 | 1d | ADMIN | Sophie Harder | [6 empty] | 145SS -5d
DO - Get Hot Water Rebate | Not Started | 2024-11-21 | 2024-11-21 | 1d | ADMIN | Sophie Harder | [6 empty] | 128
Req Full Turn Key Package | Not Started | 2024-11-22 | 2024-11-22 | 1d | TURN KEY | Lovering Installations QLD | [6 empty] | 127, 121
Req Painter Touch Ups | Not Started | 2024-11-22 | 2024-11-22 | 1d | PAINTER | Painter | [6 empty] | 121, 127, 118
Req Solar Panel Commisions | Not Started | 2024-11-22 | 2024-11-22 | 1d | SOLAR | Open Electrical | [6 empty] | 127
CERTIFICATE - Electrician | Not Started | 2024-11-22 | 2024-11-22 | 1d | ADMIN | Sophie Harder | [6 empty] | 127
Req Ceiling Insulation | Not Started | 2024-11-25 | 2024-11-25 | 1d | INSULATION | Austral Insulation | [6 empty] | 127, 135
Req Vinyl Floor | Not Started | 2024-11-25 | 2024-11-25 | 1d | FLOOR COVERINGS | Joii Flooring | [6 empty] | 133
Req Window Handover Service | Not Started | 2024-11-25 | 2024-11-25 | 1d | WINDOWS | Southern Star Windows | [6 empty] | 133
SPO - Insulation Spread Ceiling Insulation | Not Started | 2024-11-25 | 2024-11-25 | 1d | INSULATION | Austral Insulation | [6 empty] | 127, 135
Do - Put Termite Sticker In MeterBox and Kitchen Cupboard | Not Started | 2024-11-26 | 2024-11-26 | 1d | SUPERVISOR | Andrew Clement | [6 empty] | 145SS -1d
Req Builders Clean | Not Started | 2024-11-26 | 2024-11-26 | 1d | HOUSE CLEAN | A1 Builders Finals/Services Group | [6 empty] | 127, 135, 138, 126
CERTIFICATE - Ceiling Insulation | Not Started | 2024-11-26 | 2024-11-26 | 1d | ADMIN | Sophie Harder | [6 empty] | 137
PHOTO - Practical Completion | Not Started | 2024-11-27 | 2024-11-27 | 1d | SUPERVISOR | Andrew Clement | [6 empty] | 142
Do Council Final Inspection | Not Started | 2024-11-27 | 2024-11-27 | 1d | PRIVATE CERTIFIER | Andrew Clement | [6 empty] | 142
GET - Form 11/21 from Certifier | Not Started | 2024-11-28 | 2024-11-28 | 1d | ADMIN | Sophie Harder | [6 empty] | 145
CREATE - Builder Confirmation | Not Started | 2024-11-28 | 2024-11-28 | 1d | ADMIN | Sophie Harder | [6 empty] | 145
GET - Engineer For Future Ceiling | Not Started | 2024-11-28 | 2024-11-28 | 1d | ADMIN | Sophie Harder | [6 empty] | 145
GET - SDA Site Density Report | Not Started | 2024-11-28 | 2024-11-28 | 1d | ADMIN | Sophie Harder | [6 empty] | 145
CREATE - Evacuation Plan | Not Started | 2024-11-28 | 2024-11-28 | 1d | ADMIN | Sophie Harder | [6 empty] | 145
CLAIM - Practical Completion | Not Started | 2024-11-28 | 2024-12-04 | 5d | ADMIN | Sophie Harder | [6 empty] | 145
DO - NDIS Final Inspection | Not Started | 2024-11-29 | 2024-11-29 | 1d | NDIS | Andrew Clement | [6 empty] | 145, 147, 150
DO - Final Payment has been made, Organize Handover house | Not Started | 2024-12-05 | 2024-12-05 | 1d | SUPERVISOR | Andrew Clement | [6 empty] | 145, 151

## Comments
Row 152 | We require the following evidence prior to attending site: • Form 11/21 from Building Certifier (Final Certification) • SDA Provider - Site density of SDA Complies with density requirements • Architect – Site Plan (including common areas) and Final Internal Floor Plan • Builder/Architect/Fire Engineer – Emergency Evacuation Plan (also must be displayed in each dwelling at time of final inspection) • Builder – letter confirmation in regard to the provision of: • Slip resistance to all areas (applies to all areas). Applies to all design categories • Reinforcement of 12mm thick, extending to height of 2100mm or concrete/masonry walls. Applies to all design categories • Carpet pile height or thickness of not more than 11mm and backing not more than 4mm. Applies to all design categories • Where ducted air-conditioning is provided, zoning of habitable rooms is provided. Applies to FA and HPS • Internet connection has been provided throughout the house. Applies to FA and HPS • Qualified, Insured and Practising Structural Engineer – letter that states that the participants bedroom has been inspected and have been provided with power and inbuilt structure capable of installation of a minimum 250kg load capacity, constant charge ceiling hoist which is capable of going across the bed and down the bed. Applies to HPS We require the above evidence at least 2 days prior to us attending site. Should you have any questions, please do not hesitate to contact. | Robert Harder | 09/07/24 6:41 AM