## Construction SM Final
title | category | stage | Start | Complete | duration | stage$type | supplier_category_id | supplier_category | supplier_category$type | scan | photo | audit_checklist | check | note | confirm | supplier_confirm | milestone | ted | flavour_id | id | sys_type_id | deleted | construction_type | colour_id | colour | colour$type | parent_id | parent | parent$type | drive_id | folder_id | Predecessors
SITE COSTS | Construction | Site Costs | 2023-06-23 | 2023-11-29 | 114d | 106 | [12 empty] | 621 | 621 | 99 |  | N/A
Req Tree Removal | Construction | Site Costs | 2023-06-23 | 2023-06-23 | 1d | 106 | 209 | SITE WORKS | 69 | [9 empty] | 514 | 514 | 99 | [10 empty] | 4SS -1d
Req Silt Barrier and Gravel Entry | Construction | Site Costs | 2023-06-26 | 2023-06-26 | 1d | 106 | 159 | SILT BARRIER | 69 | [9 empty] | 451 | 451 | 99 | [10 empty] | 4SS
Req Site Cut | Construction | Site Costs | 2023-06-26 | 2023-06-26 | 1d | 106 | 209 | SITE WORKS | 69 |  | TRUE | [7 empty] | 597 | 597 | 99
Req OHSE/WHSE House | Construction | Site Costs | 2023-06-26 | 2023-06-26 | 1d | 106 | 212 | OFFICE ADMIN | 69 | TRUE |  |  |  | <h2 style="box-sizing: border-box; scroll-behavior: smooth; margin: 0px 0px 12px; padding: 0px; color: rgb(8, 24, 51); font-family: Poppins, sans-serif; font-weight: 700; letter-spacing: normal; font-size: 32px; line-height: 34px; font-style: normal; font-variant-ligatures: normal; font-variant-caps: normal; orphans: 2; text-align: start; text-indent: 0px; text-transform: none; white-space: normal; widows: 2; word-spacing: 0px; -webkit-text-stroke-width: 0px; background-color: rgb(255, 255, 255); text-decoration-thickness: initial; text-decoration-style: initial; text-decoration-color: initial;"><b><span style="font-size:10.0pt;font-family:&quot;Arial&quot;,sans-serif; mso-fareast-font-family:&quot;Times New Roman&quot;;color:#081833;mso-font-kerning:0pt; mso-ligatures:none;mso-fareast-language:EN-AU">Occupational Health, Safety &amp; Environmental (OHSE/WHSE) Management System</span></b></h2> |  |  |  |  | 534 | 534 | 99 | [10 empty] | 4SS
DRIVEWAY |  |  | 2023-09-26 | 2023-10-02 | 5d | [26 empty] | 180, 151, 33
Req Driveway Kerb Cut Out | Construction | Site Costs | 2023-09-26 | 2023-09-26 | 1d | 106 | 217 | DRIVEWAY | 69 | [9 empty] | 306 | 306 | 99
Req Driveway Prep/ Site Clean | Construction | Site Costs | 2023-09-27 | 2023-09-27 | 1d | 106 | 217 | DRIVEWAY | 69 | [9 empty] | 307 | 307 | 99 | [10 empty] | 7
Req Driveway Steel Reo | Construction | Site Costs | 2023-09-27 | 2023-09-27 | 1d | 106 | 217 | DRIVEWAY | 69 | [9 empty] | 308 | 308 | 99 | [10 empty] | 8SS
Req Driveway Deco to site | Construction | Site Costs | 2023-09-27 | 2023-09-27 | 1d | 106 | 217 | DRIVEWAY | 69 | [9 empty] | 304 | 304 | 99 | [10 empty] | 8SS
Req Driveway Concretor | Construction | Site Costs | 2023-09-28 | 2023-09-28 | 1d | 106 | 217 | DRIVEWAY | 69 | TRUE |  |  | TRUE | <p>Req Book Driveway Completion Inspection GOLD COAST MUST ORDER IN ADVANCE</p><p>Scan Driveway Completion Report</p><p>Scan Driveway inspection</p> |  |  |  |  | 301 | 301 | 99 | [10 empty] | 7, 8, 9
Req Driveway Concrete | Construction | Site Costs | 2023-09-28 | 2023-09-28 | 1d | 106 | 217 | DRIVEWAY | 69 | [9 empty] | 299 | 299 | 99 | [10 empty] | 11SS
Req Driveway Concrete Pump | Construction | Site Costs | 2023-09-28 | 2023-09-28 | 1d | 106 | 217 | DRIVEWAY | 69 | [9 empty] | 300 | 300 | 99 | [10 empty] | 11SS
Req Driveway Covercreted | Construction | Site Costs | 2023-09-29 | 2023-09-29 | 1d | 106 | 217 | DRIVEWAY | 69 | [9 empty] | 302 | 302 | 99 | [10 empty] | 11
Req Covercrete Alfresco / Patio | Construction | Site Costs | 2023-09-29 | 2023-10-02 | 2d | 106 | 217 | DRIVEWAY | 69 | [9 empty] | 283 | 283 | 99 | [10 empty] | 11
Req Epoxy Alfresco/Porch/Garage | Construction | Site Costs | 2023-09-29 | 2023-10-02 | 2d | 106 | 217 | DRIVEWAY | 69 | [9 empty] | 319 | 319 | 99 | [10 empty] | 11
SITE POWER - GAS - TEMP FENCING |  |  | 2023-06-27 | 2023-11-29 | 112d
Req Temp Power Pole | Construction | Site Costs | 2023-06-27 | 2023-11-29 | 112d | 106 | 115 | ELECTRICAL | 69 | [9 empty] | 496 | 496 | 99 | [10 empty] | 4
Req Toilet To Site | Construction | Site Costs | 2023-06-27 | 2023-10-30 | 90d | 106 | 116 | TOILETS | 69 | [9 empty] | 512 | 512 | 99 | [10 empty] | 4
Req Permanent Power Pole | Construction | Site Costs | 2023-06-27 | 2023-06-27 | 1d | 106 | 115 | ELECTRICAL | 69 | [9 empty] | 406 | 406 | 99 | [10 empty] | 4
Req Gas Lead in from Street Natural Gas | Construction | Site Costs | 2023-06-27 | 2023-07-17 | 15d | 106 | 196 | GAS | 69 | [9 empty] | 348 | 348 | 99 | [10 empty] | 4
Req Temporary Fencing | Construction | Site Costs | 2023-06-27 | 2023-11-29 | 112d | 106 | 144 | FENCING | 69 | [9 empty] | 197 | 197 | 99 | [10 empty] | 4
Do Builders Sign | Construction | Site Costs | 2023-06-27 | 2023-06-27 | 1d | 106 | 117 | SUPERVISING | 69 |  | TRUE | [7 empty] | 211 | 211 | 99 | [10 empty] | 4
Req Power To Site | Construction | Site Costs | 2023-06-27 | 2023-06-27 | 1d | 106 | 122 | TEMPORARY POWER | 69 | [9 empty] | 420 | 420 | 99 | [10 empty] | 4
Req Soil Removal | Construction | Site Costs | 2023-06-27 | 2023-06-27 | 1d | 106 | 209 | SITE WORKS | 69 | [9 empty] | 470 | 470 | 99 | [10 empty] | 4
LANDSCAPING |  |  | 2023-10-03 | 2023-10-09 | 5d | [26 empty] | 6
Req Retaining Wall | Construction | Site Costs | 2023-10-03 | 2023-10-04 | 2d | 106 | 146 | RETAINING WALL | 69 |  |  |  | TRUE | <p>if over 1 meter require a engineer certiifcate, scan in</p> |  |  |  |  | 435 | 435 | 99
Req Seepage Trench For Retaining Wall | Construction | Site Costs | 2023-10-03 | 2023-10-03 | 1d | 106 | 150 | DRAINER | 69 |  |  |  |  | <p>only if developer retaining wall - drawn on plan </p> |  |  |  |  | 444 | 444 | 99 |  | Supplier
Req Fence | Construction | Site Costs | 2023-10-03 | 2023-10-04 | 2d | 106 | 144 | FENCING | 69 |  | TRUE | TRUE |  | <p>fire it off roof completion, audit fence</p> |  |  |  |  | 330 | 330 | 99
Req Landscaping | Construction | Site Costs | 2023-10-05 | 2023-10-09 | 3d | 106 | 145 | LANDSCAPING | 69 |  | TRUE | [7 empty] | 374 | 374 | 99 | [10 empty] | 29
SITE CLEAN |  |  | 2023-07-18 | 2023-10-09 | 60d
Req Skip Bin - Driveway | Construction | Site Costs | 2023-10-03 | 2023-10-09 | 5d | 106 | 123 | SITE CLEAN | 69 | [9 empty] | 594 | 594 | 99 | [10 empty] | 6
Req Site Clean After Plasterboard & Brickwork | Construction | Site Costs | 2023-09-25 | 2023-09-25 | 1d | 106 | 123 | SITE CLEAN | 69 | [9 empty] | 452 | 452 | 99 | [10 empty] | 151, 180, 175
Req Site Clean After Roof | Construction | Site Costs | 2023-08-15 | 2023-08-15 | 1d | 106 | 123 | SITE CLEAN | 69 | [9 empty] | 454 | 454 | 99 | [10 empty] | 121, 120
Req Site Clean Final | Construction | Site Costs | 2023-10-03 | 2023-10-03 | 1d | 106 | 123 | SITE CLEAN | 69 | [9 empty] | 455 | 455 | 99 | [10 empty] | 6
Req Landscape Prep/Final Site Clean | Construction | Site Costs | 2023-10-03 | 2023-10-03 | 1d | 106 | 123 | SITE CLEAN | 69 |  |  |  | TRUE | <p>Check All Feild Gully's As Visable As Per Plan</p><p>Check All Field Gully's Are Free Of Breaks and Debris</p><p>Req Landscape Practical Completion Report</p> |  |  |  |  | 373 | 373 | 99 | [10 empty] | 6
Req Level Site After Slab Poured/Soil Removal | Construction | Site Costs | 2023-07-18 | 2023-07-18 | 1d | 106 | 123 | SITE CLEAN | 69 |  |  |  | TRUE | <p>Check All Feild Gully's As Visable As Per Plan</p> |  |  |  |  | 378 | 378 | 99 | [10 empty] | 47
SCAFFOLD |  |  | 2023-08-04 | 2023-10-12 | 50d | [26 empty] | 89
Req Balcony Guard | Construction | Site Costs | 2023-08-04 | 2023-08-14 | 7d | 106 | 138 | SCAFFOLD | 69 |  |  |  |  | <p>If needed for Balacony</p> |  |  |  |  | 216 | 216 | 99
Req Lower Roof Walkway | Construction | Site Costs | 2023-08-04 | 2023-08-23 | 14d | 106 | 138 | SCAFFOLD | 69 | [9 empty] | 381 | 381 | 99
Req Rafter Fallguard - On Roof | Construction | Site Costs | 2023-08-04 | 2023-10-05 | 45d | 106 | 138 | SCAFFOLD | 69 |  |  |  |  | <p>on roof as can install onroof saffold </p> |  |  |  |  | 429 | 429 | 99
Req Rafter Fallguard Highset Homes | Construction | Site Costs | 2023-08-04 | 2023-08-16 | 9d | 106 | 138 | SCAFFOLD | 69 |  |  |  |  | <p>to put roof on </p> |  |  |  |  | 430 | 430 | 99
Req Rafter Fallguard Lowset Homes | Construction | Site Costs | 2023-08-04 | 2023-08-16 | 9d | 106 | 138 | SCAFFOLD | 69 |  |  |  |  | <p>to put roof on for low set</p> |  |  |  |  | 431 | 431 | 99
Req Sliding Door Fall Protection | Construction | Site Costs | 2023-08-04 | 2023-08-17 | 10d | 106 | 138 | SCAFFOLD | 69 | [9 empty] | 464 | 464 | 99
Req Void Platform | Construction | Site Costs | 2023-08-04 | 2023-10-12 | 50d | 106 | 138 | SCAFFOLD | 69 | [9 empty] | 520 | 520 | 99
Req Steel Scaffold | Construction | Site Costs | 2023-08-04 | 2023-08-31 | 20d | 106 | 138 | SCAFFOLD | 69 | [9 empty] | 486 | 486 | 99
SLAB | Construction | Slab | 2023-06-27 | 2023-07-17 | 15d | 106 | [12 empty] | 643 | 643 | 99 |  | N/A
Req Surveyor to Setout Wafflepod | Construction | Slab | 2023-06-27 | 2023-06-27 | 1d | 106 | 148 | SURVEYOR | 69 | TRUE |  |  | TRUE | <p>Scan Surveyor Certificate SCAN ( only required for built to boundary or height </p><p>Scan setout inspection</p> |  |  |  |  | 494 | 494 | 99 | [10 empty] | 4
Req Concretor To Pour Piers | Construction | Slab | 2023-06-28 | 2023-06-28 | 1d | 106 | 104 | CONCRETOR | 69 | TRUE |  |  |  | <p>Scan Engineers Footing Inspection Site Report</p><p>Scan Eng Footing Inspection Certificate</p> |  |  |  |  | 279 | 279 | 99 | [10 empty] | 48
Req Concrete For Piers | Construction | Slab | 2023-06-28 | 2023-06-28 | 1d | 106 | 110 | CONCRETE | 69 | [9 empty] | 265 | 265 | 99 | [10 empty] | 49SS
Req Concrete Pump For Piers | Construction | Slab | 2023-06-28 | 2023-06-28 | 1d | 106 | 110 | CONCRETE | 69 | [9 empty] | 270 | 270 | 99 | [10 empty] | 49SS
Req Engineer Inspection Piers | Construction | Slab | 2023-06-28 | 2023-06-28 | 1d | 106 | 134 | ENGINEER | 69 | [9 empty] | 318 | 318 | 99 | [10 empty] | 49SS
Req Machinery For Piers | Construction | Slab | 2023-06-28 | 2023-06-28 | 1d | 106 | 167 | MACHINERY | 69 | [9 empty] | 383 | 383 | 99 | [10 empty] | 49SS
Req Screw Piers | Construction | Slab | 2023-06-28 | 2023-06-28 | 1d | 106 | 104 | CONCRETOR | 69 | [9 empty] | 440 | 440 | 99 | [10 empty] | 48
Req Steel For Concrete Block Slab Base Buildup |  | Slab | 2023-06-29 | 2023-06-29 | 1d | 106 | 187 | STEEL | 69 | [9 empty] | 638 | 638 | 99 | [10 empty] | 56SS
Req Concretor for Footing Blocks Slab Base Buildup |  | Slab | 2023-06-29 | 2023-06-29 | 1d | 106 | 104 | CONCRETOR | 69 | [9 empty] | 634 | 634 | 99 | [10 empty] | 49, 54
Req Concrete Footings Blocks Slab Base Buildup |  | Slab | 2023-06-29 | 2023-06-29 | 1d | 106 | 104 | CONCRETOR | 69 | [9 empty] | 636 | 636 | 99 | [10 empty] | 56SS
Req Concrete Blocks Slab Base Buildup |  | Slab | 2023-06-29 | 2023-06-29 | 1d | 106 | 110 | CONCRETE | 69 | [9 empty] | 630 | 630 | 99 | [10 empty] | 56SS
Req Concrete Pump Footings | Construction | Slab | 2023-06-29 | 2023-06-29 | 1d | 106 | 129 | CONCRETE PUMPING | 69 | [9 empty] | 268 | 268 | 99 | [10 empty] | 60SS
Req Concretor for Footings | Construction | Slab | 2023-06-29 | 2023-06-29 | 1d | 106 | 129 | CONCRETE PUMPING | 69 | [9 empty] | 272 | 272 | 99 | [10 empty] | 54, 49
SPO - Surveyor To Repin After Piers | Construction | Slab | 2023-06-29 | 2023-06-29 | 1d | 106 | 148 | SURVEYOR | 69 | [9 empty] | 194 | 194 | 99 | [10 empty] | 54, 49
Req Blocklayer Concrete Blocks Slab Base Buildup |  | Slab | 2023-06-30 | 2023-07-03 | 2d | 106 | 102 | BRICKLAYER | 69 | [9 empty] | 629 | 629 | 99 | [10 empty] | 58, 56
Req Concretor for Concrete Blocks Slab Base Buildup |  | Slab | 2023-07-04 | 2023-07-04 | 1d | 106 | 104 | CONCRETOR | 69 | [9 empty] | 631 | 631 | 99 | [10 empty] | 65SS
Req Concrete Pump for Core Fill Slab Base Buildup |  | Slab | 2023-07-04 | 2023-07-04 | 1d | 106 | 104 | CONCRETOR | 69 | [9 empty] | 632 | 632 | 99 | [10 empty] | 65SS, 63SS
Req Inspection Concrete Blocks Slab Base Buildup |  | Slab | 2023-07-04 | 2023-07-04 | 1d | 106 | 104 | CONCRETOR | 69 | [9 empty] | 637 | 637 | 99 | [10 empty] | 62
Req Concrete Core Fill Slab Base Buildup |  | Slab | 2023-07-04 | 2023-07-04 | 1d | 106 | 110 | CONCRETE | 69 | [9 empty] | 633 | 633 | 99 | [10 empty] | 65SS, 63SS
Req Drainage Concrete Block Slab Base Buildup |  | Slab | 2023-07-05 | 2023-07-05 | 1d | 106 | 104 | CONCRETOR | 69 | [9 empty] | 635 | 635 | 99 | [10 empty] | 63
Req Waterproofing Concrete Block Slab Base Buildup |  | Slab | 2023-07-05 | 2023-07-05 | 1d | 106 | 104 | CONCRETOR | 69 | [9 empty] | 639 | 639 | 99 | [10 empty] | 63
Req Backfill Concretor Block Base Buildup |  | Slab | 2023-07-06 | 2023-07-06 | 1d | 106 | 104 | CONCRETOR | 69 | [9 empty] | 628 | 628 | 99 | [10 empty] | 68
Req Bobcat To Back Fill Build Up | Construction | Slab | 2023-07-06 | 2023-07-06 | 1d | 106 | 167 | MACHINERY | 69 | [9 empty] | 228 | 228 | 99 | [10 empty] | 69SS
Req Electrician Underground | Construction | Slab | 2023-07-07 | 2023-07-07 | 1d | 106 | 115 | ELECTRICAL | 69 |  |  |  | TRUE | <p>Check Make Sure Earth Wire is Connected to Steel Mesh</p><p>Confirm Power is On Site 6 days </p><p>Do New Power Connection Application (Check Lead In Is Done on Site)</p><p>Confirm Energy Provider has Received Paper Work</p><p>Check Mains to Property is inside Brickwork</p> |  |  |  |  | 316 | 316 | 99 | [10 empty] | 73SS
Req NBN/OPTIC Lead-in | Construction | Slab | 2023-07-07 | 2023-07-07 | 1d | 106 | 149 | TELSTRA | 69 |  |  |  | TRUE | <p>Check the fibre optic/NBN conduit is clear</p> |  |  |  |  | 391 | 391 | 99 | [10 empty] | 73SS
Req Drainer for Drains Wafflepod | Construction | Slab | 2023-07-07 | 2023-07-07 | 1d | 106 | 150 | DRAINER | 69 | TRUE |  |  |  | <p>Scan Plumbing and Drainage Installation Certificate</p><p>Scan Storm Water Certificate</p><p>Scan As Constructed Drainage Plan</p> |  |  |  |  | 298 | 298 | 99 | [10 empty] | 54, 49, 69, 68
Do Plumbing Drainage Inspection | Construction | Slab | 2023-07-07 | 2023-07-07 | 1d | 106 | 106 | PRIVATE CERTIFIER | 69 | TRUE | [8 empty] | 188 | 188 | 99 | [10 empty] | 73FF
Req Pods and Steel For Wafflepod | Construction | Slab | 2023-07-10 | 2023-07-10 | 1d | 106 | 320 | STEEL / PODS / SAND | 69 | [9 empty] | 417 | 417 | 99 | [10 empty] | 73, 63
Req Bedding Sand To Site | Construction | Slab | 2023-07-10 | 2023-07-10 | 1d | 106 | 320 | STEEL / PODS / SAND | 69 | [9 empty] | 221 | 221 | 99 | [10 empty] | 73, 69SS
Req Surveyor To Repin After Drains | Construction | Slab | 2023-07-10 | 2023-07-10 | 1d | 106 | 148 | SURVEYOR | 69 | [9 empty] | 193 | 193 | 99 | [10 empty] | 73
Req Concretor to Setup Wafflepod | Construction | Slab | 2023-07-11 | 2023-07-11 | 1d | 106 | 104 | CONCRETOR | 69 | [9 empty] | 281 | 281 | 99 | [10 empty] | 69, 73, 75
Req Bobcat For Sand Up | Construction | Slab | 2023-07-11 | 2023-07-11 | 1d | 106 | 167 | MACHINERY | 69 | [9 empty] | 227 | 227 | 99 | [10 empty] | 76, 69, 78SS
Req Concretor For Complete Slab Labour And Materials | Construction | Slab | 2023-07-11 | 2023-07-14 | 4d | 106 | 104 | CONCRETOR | 69 |  | TRUE |  |  | <p>Scan Slab Audit Checklist and scan</p><p>Scan Engineers Slab Inspection Site Report</p><p>Scan Eng Slab Inspection Certificate</p> |  |  | TRUE |  | 273 | 273 | 99 | [10 empty] | 77
Req Concretor to Pour Slab Wafflepod | Construction | Slab | 2023-07-12 | 2023-07-12 | 1d | 106 | 104 | CONCRETOR | 69 | TRUE | TRUE | TRUE |  | <p>Scan Slab Audit Checklist and scan</p><p>Scan Engineers Slab Inspection Site Report</p><p>Scan Eng Slab Inspection Certificate</p> |  |  | TRUE |  | 280 | 280 | 99 | [10 empty] | 78
Req Concrete for Wafflepod | Construction | Slab | 2023-07-12 | 2023-07-12 | 1d | 106 | 110 | CONCRETE | 69 | [9 empty] | 267 | 267 | 99 | [10 empty] | 81SS
Req Concrete Pump for Wafflepod | Construction | Slab | 2023-07-12 | 2023-07-12 | 1d | 106 | 129 | CONCRETE PUMPING | 69 | [9 empty] | 271 | 271 | 99 | [10 empty] | 81SS
Req Termi-Mesh Penetrations | Construction | Slab | 2023-07-13 | 2023-07-13 | 1d | 106 | 155 | TERMITE PROTECTION | 69 | [9 empty] | 593 | 593 | 99 | [10 empty] | 78SS, 80FF -1d
Req Smart-Film Penetrations | Construction | Slab | 2023-07-13 | 2023-07-13 | 1d | 106 | 155 | TERMITE PROTECTION | 69 | TRUE | [8 empty] | 465 | 465 | 99 | [10 empty] | 78SS, 80FF -1d
Req Waffle Pod Inspection | Construction | Slab | 2023-07-13 | 2023-07-13 | 1d | 106 | 134 | ENGINEER | 69 | [9 empty] | 463 | 463 | 99 | [10 empty] | 78FF, 80FF -1d
Do Generate Meterbox Documentation | Construction | Slab | 2023-07-17 | 2023-07-17 | 1d | 106 | 212 | OFFICE ADMIN | 69 | TRUE |  |  | TRUE | [5 empty] | 186 | 186 | 99 | [10 empty] | 71FS +5d
Req Waterproof Slab Edge | Construction | Slab | 2023-07-17 | 2023-07-17 | 1d | 106 | 142 | WATER PROOFER | 69 | [9 empty] | 530 | 530 | 99 | [10 empty] | 80, 81
FRAME | Construction | Frame | 2023-07-18 | 2023-08-03 | 13d | 106 | [12 empty] | 627 | 627 | 99 |  | N/A | [8 empty] | 47
Req Steel Posts | Construction | Frame | 2023-07-18 | 2023-07-18 | 1d | 106 | 157 | STEEL BEAMS/POSTS | 69 | [9 empty] | 484 | 484 | 99 | [10 empty] | 93SS
Req Structural Steel | Construction | Frame | 2023-07-18 | 2023-07-18 | 1d | 106 | 157 | STEEL BEAMS/POSTS | 69 | [9 empty] | 490 | 490 | 99 | [10 empty] | 93SS
Req Frame Material First Floor | Construction | Frame | 2023-07-18 | 2023-07-18 | 1d | 106 | 178 | TIMBER FRAME | 69 | [9 empty] | 339 | 339 | 99 | [10 empty] | 93SS
Req Frame Material Ground Floor | Construction | Frame | 2023-07-18 | 2023-07-18 | 1d | 106 | 178 | TIMBER FRAME | 69 | [9 empty] | 340 | 340 | 99
Req Prenail Frame First Floor | Construction | Frame | 2023-07-18 | 2023-07-18 | 1d | 106 | 178 | TIMBER FRAME | 69 | [9 empty] | 423 | 423 | 99 | [10 empty] | 95SS
Req Prenail Frame Ground Floor | Construction | Frame | 2023-07-18 | 2023-07-18 | 1d | 106 | 178 | TIMBER FRAME | 69 | [9 empty] | 424 | 424 | 99
Req Steel Frame First Floor | Construction | Frame | 2023-07-18 | 2023-07-18 | 1d | 106 | 178 | TIMBER FRAME | 69 | [9 empty] | 482 | 482 | 99 | [10 empty] | 97SS
Req Steel Frame Ground Floor | Construction | Frame | 2023-07-18 | 2023-07-18 | 1d | 106 | 178 | TIMBER FRAME | 69 | [9 empty] | 483 | 483 | 99 | [10 empty] | 93SS
Req Frame Material Structural Floor First Floor | Construction | Frame | 2023-07-18 | 2023-07-18 | 1d | 106 | 207 | TIMBER FLOORING | 69 | [9 empty] | 341 | 341 | 99 | [10 empty] | 93SS
Req Structural Floor Sheeting First Floor | Construction | Frame | 2023-07-18 | 2023-07-18 | 1d | 106 | 207 | TIMBER FLOORING | 69 | [9 empty] | 488 | 488 | 99 | [10 empty] | 93SS
Req Structural Floor Sheeting Ground Floor | Construction | Frame | 2023-07-18 | 2023-07-18 | 1d | 106 | 207 | TIMBER FLOORING | 69 | [9 empty] | 489 | 489 | 99 | [10 empty] | 93SS
Req Prenail Frame And Trusses | Construction | Frame | 2023-07-19 | 2023-07-19 | 1d | 106 | 178 | TIMBER FRAME | 69 | TRUE |  |  |  | <p>Scan Truss Certificate</p> |  |  |  |  | 422 | 422 | 99 | [10 empty] | 94
Req Carpenter Ground Floor | Construction | Frame | 2023-07-19 | 2023-07-25 | 5d | 106 | 101 | CARPENTER | 69 | TRUE | TRUE | TRUE |  | <p>Structural Frame Audit Checklist and scan</p><p>Scan Frame Inspection Report</p><p>Scan for 15 Lintel Layout</p><p>Scan Frame Inspection Certificate</p> |  |  |  |  | 247 | 247 | 99 | [10 empty] | 93, 95, 97
Req Perimeter Fallguard | Construction | Frame | 2023-07-26 | 2023-07-28 | 3d | 106 | 138 | SCAFFOLD | 69 |  |  |  |  | <p>capenter to install floor sheeting and first floor frame</p> |  |  |  |  | 405 | 405 | 99 | [10 empty] | 102
Req Frame Hardware | Construction | Frame | 2023-07-26 | 2023-07-26 | 1d | 106 | 178 | TIMBER FRAME | 69 | [9 empty] | 338 | 338 | 99 | [10 empty] | 102SS, 106SS
Req Timber External Deck | Construction | Frame | 2023-07-26 | 2023-07-26 | 1d | 106 | 178 | TIMBER FRAME | 69 | [9 empty] | 509 | 509 | 99 | [10 empty] | 104SS
Req Carpenter First Floor | Construction | Frame | 2023-07-26 | 2023-08-01 | 5d | 106 | 101 | CARPENTER | 69 | TRUE | TRUE | TRUE |  | <p>Structural Frame Audit Checklist and scan </p><p>Scan Frame Inspection Report</p><p>Scan for 15 Lintel Layout</p><p>Scan Form 15 - Floor Joist</p><p>n Form 15 Timber Lintel LayoutScan Frame Inspection Certificate</p> |  |  |  |  | 244 | 244 | 99 | [10 empty] | 102, 92, 94, 99, 100
Req Crane For Structural Floor First Floor | Construction | Frame | 2023-07-26 | 2023-07-26 | 1d | 106 | 130 | CRANE | 69 | [9 empty] | 285 | 285 | 99 | [10 empty] | 102
Req Crane Frame First Floor | Construction | Frame | 2023-07-26 | 2023-07-26 | 1d | 106 | 130 | CRANE | 69 | [9 empty] | 286 | 286 | 99 | [10 empty] | 102
Req Welding Of Steels Beams | Construction | Frame | 2023-07-31 | 2023-07-31 | 1d | 106 | 157 | STEEL BEAMS/POSTS | 69 | [9 empty] | 533 | 533 | 99 | [10 empty] | 102FF -1d, 106FF -1d
Measure Internal Stairs | Construction | Frame | 2023-07-31 | 2023-07-31 | 1d | 106 | 170 | STAIRS | 69 | [9 empty] | 207 | 207 | 99 | [10 empty] | 102FF -1d, 106FF -1d
Do Frame Inspection | Construction | Frame | 2023-08-02 | 2023-08-02 | 1d | 106 | 106 | PRIVATE CERTIFIER | 69 | [9 empty] | 185 | 185 | 99 | [10 empty] | 102, 106
Req Waterproofer For Veranda Wall/Floor Junction | Construction | Frame | 2023-08-02 | 2023-08-02 | 1d | 106 | 142 | WATER PROOFER | 69 | [9 empty] | 531 | 531 | 99 | [10 empty] | 106
Req Carpenter Deck Labour | Construction | Frame | 2023-08-02 | 2023-08-03 | 2d | 106 | 101 | CARPENTER | 69 | [9 empty] | 243 | 243 | 99 | [10 empty] | 106
Req Crane Roof Trusses | Construction | Frame | 2023-07-28 | 2023-07-28 | 1d | 106 | 130 | CRANE | 69 | [9 empty] | 287 | 287 | 99 | [10 empty] | 115SS, 116SS
Req Steel Roof Trusses | Construction | Frame | 2023-07-28 | 2023-07-28 | 1d | 106 | 147 | TRUSSES | 69 | [9 empty] | 485 | 485 | 99 | [10 empty] | 106SS +2d, 102SS +2d
Req Roof Trusses | Construction | Frame | 2023-07-28 | 2023-07-28 | 1d | 106 | 147 | TRUSSES | 69 | TRUE |  |  |  | <p>Scan Truss Certificate</p> |  |  |  |  | 439 | 439 | 99 | [10 empty] | 106SS +2d, 102SS +2d
ENCLOSED | Construction | Enclosed | 2023-08-02 | 2023-08-30 | 21d | 106 | [12 empty] | 625 | 625 | 99 |  | N/A
Req Hang-on Platform | Construction | Enclosed | 2023-08-02 | 2023-08-15 | 10d | 106 | 138 | SCAFFOLD | 69 |  |  |  |  | <p> lowerset if over 3 meter in height</p> |  |  |  |  | 354 | 354 | 99 | [10 empty] | 102, 106
Req Fascia And Gutter | Construction | Enclosed | 2023-08-03 | 2023-08-03 | 1d | 106 | 321 | ROOF | 69 | [9 empty] | 328 | 328 | 99 | [10 empty] | 102, 106, 118SS +1d
Req Fascia and Gutter and Colorbond Roof | Construction | Enclosed | 2023-08-03 | 2023-08-14 | 8d | 106 | 321 | ROOF | 69 | TRUE | TRUE |  |  | <p>Scan Roofing Certificate</p> |  |  | TRUE |  | 329 | 329 | 99 | [10 empty] | 102, 106, 118SS +1d
Req Tile Roof | Construction | Enclosed | 2023-08-04 | 2023-08-07 | 2d | 106 | 321 | ROOF | 69 | TRUE | TRUE |  |  | <p>Scan Roofing Certificate</p> |  |  | TRUE |  | 380 | 380 | 99 | [10 empty] | 102, 106, 119
Req Bricks House | Construction | Enclosed | 2023-08-11 | 2023-08-11 | 1d | 106 | 107 | BRICKS | 69 | [9 empty] | 237 | 237 | 99 | [10 empty] | 121FS -2d, 120FS -2d
Req Smart-Film Perimeter | Construction | Enclosed | 2023-08-11 | 2023-08-11 | 1d | 106 | 155 | TERMITE PROTECTION | 69 | [9 empty] | 466 | 466 | 99 | [10 empty] | 122SS
Req Termi-Mesh Perimeter | Construction | Enclosed | 2023-08-11 | 2023-08-11 | 1d | 106 | 155 | TERMITE PROTECTION | 69 | [9 empty] | 498 | 498 | 99 | [10 empty] | 122SS
Req Brick Lintels | Construction | Enclosed | 2023-08-11 | 2023-08-11 | 1d | 106 | 184 | BRICK HARDWARE | 69 | [9 empty] | 233 | 233 | 99 | [10 empty] | 122SS
Req Windows | Construction | Enclosed | 2023-08-15 | 2023-08-15 | 1d | 106 | 103 | WINDOWS | 69 | TRUE |  |  |  | <p>Scan Glazing Certificate</p> |  |  |  |  | 538 | 538 | 99 | [10 empty] | 121, 120
Req Antenna | Construction | Enclosed | 2023-08-15 | 2023-08-15 | 1d | 106 | 186 | TURN KEY | 69 | [9 empty] | 215 | 215 | 99 | [10 empty] | 121, 120
Req Hebel External Cladding Supply | Construction | Enclosed | 2023-08-15 | 2023-08-15 | 1d | 106 | 160 | RENDER | 69 | [9 empty] | 357 | 357 | 99 | [10 empty] | 121, 120
Req Down Pipes First Floor | Construction | Enclosed | 2023-08-15 | 2023-08-15 | 1d | 106 | 321 | ROOF | 69 | [9 empty] | 295 | 295 | 99 | [10 empty] | 119, 120
Req Down Pipes Ground Floor | Construction | Enclosed | 2023-08-15 | 2023-08-15 | 1d | 106 | 321 | ROOF | 69 | [9 empty] | 296 | 296 | 99 | [10 empty] | 119, 120
Req Solar Panel For Solar Hot Water System | Construction | Enclosed | 2023-08-15 | 2023-08-15 | 1d | 106 | 333 | SOLAR | 69 | [9 empty] | 472 | 472 | 99 | [10 empty] | 121, 120
Req Solar Panels Electricity | Construction | Enclosed | 2023-08-15 | 2023-08-15 | 1d | 106 | 333 | SOLAR | 69 | [9 empty] | 473 | 473 | 99 | [10 empty] | 121, 120
Req External Doors | Construction | Enclosed | 2023-08-16 | 2023-08-16 | 1d | 106 | 135 | ENT DOORS | 69 | [9 empty] | 325 | 325 | 99 | [10 empty] | 135SS
Req External Door Handle Locks | Construction | Enclosed | 2023-08-16 | 2023-08-16 | 1d | 106 | 135 | ENT DOORS | 69 | [9 empty] | 324 | 324 | 99 | [10 empty] | 133SS
Req Carpenter Install Win/Bath/Doors | Construction | Enclosed | 2023-08-16 | 2023-08-16 | 1d | 106 | 101 | CARPENTER | 69 | [9 empty] | 249 | 249 | 99 | [10 empty] | 126
Req Hebel External Cladding Install | Construction | Enclosed | 2023-08-16 | 2023-08-22 | 5d | 106 | 160 | RENDER | 69 | [9 empty] | 356 | 356 | 99 | [10 empty] | 128
Req Measure Garage Doors | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 136 | GARAGE DOORS | 69 | [9 empty] | 385 | 385 | 99 | [10 empty] | 135
Req Hebel External Cladding Supply and Install | Construction | Enclosed | 2023-08-17 | 2023-08-24 | 6d | 106 | 160 | RENDER | 69 | [9 empty] | 358 | 358 | 99 | [10 empty] | 135
Req Soffit Hardware | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 163 | SOFFIT | 69 | [9 empty] | 467 | 467 | 99 | [10 empty] | 135
Req External Cladding | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 181 | EXTERNAL CLADDING | 69 | [9 empty] | 323 | 323 | 99 | [10 empty] | 135
Req Wall Sisilation Ground Floor | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 169 | INSULATION | 69 | [9 empty] | 525 | 525 | 99 | [10 empty] | 135
Req Supply and Install Wall Sisilation | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 169 | INSULATION | 69 | [9 empty] | 491 | 491 | 99 | [10 empty] | 135
Req Mixer Bodies For Plumber Rough In | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 191 | PLUMBING FITOFF GEAR | 69 | [9 empty] | 388 | 388 | 99 | [10 empty] | 148SS
Req Air Conditioning Rough In | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 185 | AIR CONDITIONING | 69 |  |  | TRUE |  | <p>Scan Frame and Pre Plaster Audit Checklist and scan</p> |  |  |  |  | 213 | 213 | 99 | [10 empty] | 135
Req Carpenter Straighten Frame | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 101 | CARPENTER | 69 | [9 empty] | 252 | 252 | 99 | [10 empty] | 135
Req Electrician - Prewire | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 115 | ELECTRICAL | 69 |  |  | TRUE |  | <p>Scan Frame and Pre Plaster Audit Checklist and scan</p> |  |  |  |  | 315 | 315 | 99 | [10 empty] | 135
Req NBN/OPTIC Pre Wire | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 149 | TELSTRA | 69 | [9 empty] | 392 | 392 | 99 | [10 empty] | 135
Req Plumber Rough In | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 153 | PLUMBER | 69 |  |  | TRUE |  | <p>Scan Frame and Pre Plaster Audit Checklist</p> |  |  |  |  | 416 | 416 | 99 | [10 empty] | 135
Req Gas Rough In | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 196 | GAS | 69 | [9 empty] | 349 | 349 | 99 | [10 empty] | 135
Req Bricklayer Hardware | Construction | Enclosed | 2023-08-17 | 2023-08-17 | 1d | 106 | 325 | BRICK HARDWARE | 69 | [9 empty] | 236 | 236 | 99 | [10 empty] | 151SS
Req Bricklayer Ground Floor | Construction | Enclosed | 2023-08-17 | 2023-08-23 | 5d | 106 | 102 | BRICKLAYER | 69 | [9 empty] | 596 | 596 | 99 | [10 empty] | 125, 122, 135, 123, 124
Req Carpenter Soffits Ground Floor | Construction | Enclosed | 2023-08-18 | 2023-08-21 | 2d | 106 | 101 | CARPENTER | 69 | [9 empty] | 251 | 251 | 99 | [10 empty] | 139
Req Soffit Hardware First Floor | Construction | Enclosed | 2023-08-18 | 2023-08-18 | 1d | 106 | 163 | SOFFIT | 69 | [9 empty] | 468 | 468 | 99 | [10 empty] | 139
Req Straighten External Frame Ground Floor Cladding | Construction | Enclosed | 2023-08-18 | 2023-08-18 | 1d | 106 | 101 | CARPENTER | 69 | [9 empty] | 599 | 599 | 99 | [10 empty] | 135, 140
Req Wall Sisilation First Floor | Construction | Enclosed | 2023-08-18 | 2023-08-18 | 1d | 106 | 169 | INSULATION | 69 | [9 empty] | 524 | 524 | 99 | [10 empty] | 141
Do Plumbing Rough-In Inspection | Construction | Enclosed | 2023-08-18 | 2023-08-18 | 1d | 106 | 106 | PRIVATE CERTIFIER | 69 | TRUE |  |  |  | <p>is thsi plumber inspector???</p> |  |  |  |  | 190 | 190 | 99 | [10 empty] | 148
Req Straighten External Frame First Floor Cladding | Construction | Enclosed | 2023-08-21 | 2023-08-21 | 1d | 106 | 101 | CARPENTER | 69 | [9 empty] | 598 | 598 | 99 | [10 empty] | 154, 135, 140
Req Carpenter Cladding | Construction | Enclosed | 2023-08-21 | 2023-08-23 | 3d | 106 | 101 | CARPENTER | 69 | [9 empty] | 242 | 242 | 99 | [10 empty] | 154
Req Carpenter Soffits First Floor | Construction | Enclosed | 2023-08-22 | 2023-08-29 | 6d | 106 | 101 | CARPENTER | 69 | [9 empty] | 250 | 250 | 99 | [10 empty] | 152, 139
Req Bricklayer First Floor | Construction | Enclosed | 2023-08-24 | 2023-08-25 | 2d | 106 | 102 | BRICKLAYER | 69 | [9 empty] | 235 | 235 | 99 | [10 empty] | 151
Req Hebel Render | Construction | Enclosed | 2023-08-25 | 2023-08-30 | 4d | 106 | 160 | RENDER | 69 | [9 empty] | 359 | 359 | 99 | [10 empty] | 136, 138
Req Render | Construction | Enclosed | 2023-08-28 | 2023-08-29 | 2d | 106 | 160 | RENDER | 69 | [9 empty] | 432 | 432 | 99 | [10 empty] | 151, 160
Req Render To Front Of House Only | Construction | Enclosed | 2023-08-28 | 2023-08-28 | 1d | 106 | 160 | RENDER | 69 | [9 empty] | 433 | 433 | 99 | [10 empty] | 151, 160
Req Brick/House Clean | Construction | Enclosed | 2023-08-28 | 2023-08-28 | 1d | 106 | 102 | BRICKLAYER | 69 | [9 empty] | 234 | 234 | 99 | [10 empty] | 160, 151
Req External Stairs | Construction | Enclosed | 2023-08-30 | 2023-08-30 | 1d | 106 | 170 | STAIRS | 69 | [9 empty] | 327 | 327 | 99 | [10 empty] | 162, 151, 160
Req External AJ Joints Off Scaffold | Construction | Enclosed | 2023-08-30 | 2023-08-30 | 1d | 106 | 210 | WET SEAL | 69 | [9 empty] | 321 | 321 | 99 | [10 empty] | 130, 162, 163
Req External AJ Joints | Construction | Enclosed | 2023-08-30 | 2023-08-30 | 1d | 106 | 210 | WET SEAL | 69 | [9 empty] | 320 | 320 | 99 | [10 empty] | 136, 163, 162
FIXING | Construction | Fixing | 2023-08-31 | 2023-10-13 | 32d | 106 | [12 empty] | 626 | 626 | 99 |  | N/A | [8 empty] | 117
Req Painter External House | Construction | Fixing | 2023-08-31 | 2023-09-01 | 2d | 106 | 100 | PAINTER | 69 |  | TRUE | [7 empty] | 397 | 397 | 99
Req Patio Pre Made | Construction | Fixing | 2023-08-31 | 2023-09-01 | 2d | 106 | 112 | PATIO | 69 | [9 empty] | 404 | 404 | 99
SPO - RTS Plasterboard Make Good Stair Void | Construction | Fixing | 2023-08-31 | 2023-08-31 | 1d | 106 | 161 | PLASTER BOARD | 69 | [9 empty] | 600 | 600 | 99
Req Ceiling Insulation Before Plasterboard | Construction | Fixing | 2023-08-31 | 2023-08-31 | 1d | 106 | 169 | INSULATION | 69 | [9 empty] | 259 | 259 | 99
Req Wall Insulation | Construction | Fixing | 2023-08-31 | 2023-08-31 | 1d | 106 | 169 | INSULATION | 69 |  | TRUE | [7 empty] | 523 | 523 | 99
Req External Balustrading (Supply and Install) | Construction | Fixing | 2023-08-31 | 2023-09-01 | 2d | 106 | 188 | BALUSTRADING | 69 | [9 empty] | 322 | 322 | 99
Req Plaster Board | Construction | Fixing | 2023-09-01 | 2023-09-13 | 9d | 106 | 161 | PLASTER BOARD | 69 |  | TRUE | TRUE |  | <p>pre-paint check list and scan</p> |  |  |  |  | 411 | 411 | 99 | [10 empty] | 173, 172
Req Plaster Board Delivery Highset | Construction | Fixing | 2023-09-01 | 2023-09-01 | 1d | 106 | 161 | PLASTER BOARD | 69 | [9 empty] | 412 | 412 | 99 | [10 empty] | 173, 172
SPO - Painter First Floor External ( When Scaffold is Up) | Construction | Fixing | 2023-09-04 | 2023-09-06 | 3d | 106 | 100 | PAINTER | 69 |  | TRUE | [7 empty] | 399 | 399 | 99 | [10 empty] | 169
Req Plaster Board Highset | Construction | Fixing | 2023-09-04 | 2023-09-20 | 13d | 106 | 161 | PLASTER BOARD | 69 |  | TRUE | TRUE |  | <p>pre-paint check list and scan</p> |  |  |  |  | 413 | 413 | 99 | [10 empty] | 173, 172, 176
Req Garage Doors | Construction | Fixing | 2023-09-21 | 2023-09-21 | 1d | 106 | 136 | GARAGE DOORS | 69 | TRUE | TRUE |  |  | <p>Scan Garage Door Certificate</p> |  |  | TRUE |  | 345 | 345 | 99 | [10 empty] | 175, 178
Req Pre Paint (Including Sanding) | Construction | Fixing | 2023-09-21 | 2023-09-22 | 2d | 106 | 161 | PLASTER BOARD | 69 | [9 empty] | 421 | 421 | 99 | [10 empty] | 175, 178
Req Internal Door Handles | Construction | Fixing | 2023-09-21 | 2023-09-21 | 1d | 106 | 182 | FIX-OUT MATERIALS | 69 | [9 empty] | 366 | 366 | 99 | [10 empty] | 185SS
SPO - Electrician - Cutouts | Construction | Fixing | 2023-09-21 | 2023-09-21 | 1d | 106 | 115 | ELECTRICAL | 69 | [9 empty] | 313 | 313 | 99 | [10 empty] | 175, 178
SPO - A/C Ducted - Cutouts | Construction | Fixing | 2023-09-21 | 2023-09-21 | 1d | 106 | 185 | AIR CONDITIONING | 69 | [9 empty] | 289 | 289 | 99 | [10 empty] | 175, 178
Req Internal Stairs | Construction | Fixing | 2023-09-21 | 2023-09-21 | 1d | 106 | 170 | STAIRS | 69 |  | TRUE | [7 empty] | 368 | 368 | 99 | [10 empty] | 175, 178
Req Internal Fixout | Construction | Fixing | 2023-09-21 | 2023-09-22 | 2d | 106 | 182 | FIX-OUT MATERIALS | 69 |  | TRUE | TRUE |  | <p>Scan QA Tiling and Pre-Painting Inspection Report and scan</p> |  |  |  |  | 367 | 367 | 99 | [10 empty] | 175, 178
Req Internal Ballustrating (Fully Installed) | Construction | Fixing | 2023-09-21 | 2023-09-21 | 1d | 106 | 188 | BALUSTRADING | 69 | [9 empty] | 365 | 365 | 99 | [10 empty] | 175, 178
Req Carpenter Fixout | Construction | Fixing | 2023-09-25 | 2023-09-26 | 2d | 106 | 101 | CARPENTER | 69 |  | TRUE | [7 empty] | 245 | 245 | 99 | [10 empty] | 175, 185
Req Tiles | Construction | Fixing | 2023-09-27 | 2023-09-27 | 1d | 106 | 140 | TILE | 69 | [9 empty] | 508 | 508 | 99 | [10 empty] | 187
Req Water Proofer | Construction | Fixing | 2023-09-27 | 2023-09-28 | 2d | 106 | 142 | WATER PROOFER | 69 | TRUE | TRUE |  |  | <p>Scan Water Proofer Certificate</p> |  |  | TRUE | TRUE | 528 | 528 | 99 | [10 empty] | 187
Req Kitchen | Construction | Fixing | 2023-09-27 | 2023-09-27 | 1d | 106 | 189 | CABINET MAKER | 69 |  | TRUE | [5 empty] | TRUE |  | 369 | 369 | 99 | [10 empty] | 187
SPO - Plaster Fit Cornice | Construction | Fixing | 2023-09-28 | 2023-09-28 | 1d | 106 | 161 | PLASTER BOARD | 69 | [9 empty] | 177 | 177 | 99 | [10 empty] | 190, 175, 178
Req Kitchen Benchtop Measure | Construction | Fixing | 2023-09-28 | 2023-09-28 | 1d | 106 | 189 | CABINET MAKER | 69 | [9 empty] | 371 | 371 | 99 | [10 empty] | 190
Req Laundry Tub If Stand Alone | Construction | Fixing | 2023-09-29 | 2023-09-29 | 1d | 106 | 139 | LAUNDRY TUBS | 69 | [9 empty] | 376 | 376 | 99 | [10 empty] | 195SS
Req Kitchen Bench Top Install | Construction | Fixing | 2023-09-29 | 2023-09-29 | 1d | 106 | 189 | CABINET MAKER | 69 | [9 empty] | 370 | 370 | 99 | [10 empty] | 190, 192
Req Tiler | Construction | Fixing | 2023-09-29 | 2023-10-03 | 3d | 106 | 238 | TILER | 69 |  | TRUE |  | TRUE | <p>Check Fall Of Tiles To Floor Wastes</p> |  |  |  |  | 507 | 507 | 99 | [10 empty] | 188, 189, 190
Req Undermount Sink | Construction | Fixing | 2023-10-02 | 2023-10-02 | 1d | 106 | 191 | PLUMBING FITOFF GEAR | 69 | [9 empty] | 516 | 516 | 99 | [10 empty] | 194
Req Painter Internal House | Construction | Fixing | 2023-10-04 | 2023-10-12 | 7d | 106 | 100 | PAINTER | 69 |  | TRUE | [7 empty] | 400 | 400 | 99 |  | Supplier | [8 empty] | 195
Measure Shower Screens Book Fitting | Construction | Fixing | 2023-10-04 | 2023-10-04 | 1d | 106 | 114 | SHOWER SCREENS | 69 | [9 empty] | 208 | 208 | 99 | [10 empty] | 195
Req Timber Floor (Supply and Lay) | Construction | Fixing | 2023-10-13 | 2023-10-13 | 1d | 106 | 111 | FLOOR COVERINGS | 69 | [9 empty] | 510 | 510 | 99 | [10 empty] | 197, 195
PRACTICAL COMPLETION | Construction | Practical Completion | 2023-10-16 | 2023-10-25 | 8d | 106 | [12 empty] | 623 | 623 | 99 |  | N/A | [8 empty] | 168
Req Water Tank | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 204 | WATER TANKS | 69 | TRUE | TRUE |  |  | <p>Scan Water Tank Certificate</p><p>Scan Rain Water Tank Declaration</p><p>Scan Form 7 Water Tank</p> |  |  |  |  | 529 | 529 | 99 | [10 empty] | 207SS
Req Bath | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 126 | BATHS | 69 |  |  |  | TRUE | <p>Check Plumb Dinger Connected To Bath, once bath is connected</p> |  |  |  |  | 218 | 218 | 99 | [10 empty] | 207SS
Req Pressure Wash and External Areas
Req Carpenter For Final Fitoff | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 101 | CARPENTER | 69 | [9 empty] | 246 | 246 | 99 | [10 empty] | 197, 195
Req Vinyl Sliders | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 114 | SHOWER SCREENS | 69 |  | TRUE | [7 empty] | 519 | 519 | 99 | [10 empty] | 197
Req Shower Screens | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 114 | SHOWER SCREENS | 69 | TRUE | TRUE |  |  | <p>Scan Shower Screen Certificate</p> |  |  |  |  | 447 | 447 | 99 | [10 empty] | 195
Req Electrical Items | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 132 | ELECTRICAL ITEMS | 69 | [9 empty] | 310 | 310 | 99
Req Plumber - Fit Off | Construction | Practical Completion | 2023-10-16 | 2023-10-17 | 2d | 106 | 153 | PLUMBER | 69 | TRUE |  |  |  | <p>Scan plumbing final inspection report</p><p>Scan Plumbing Final Inspection</p><p>Scan Form 7 Plumbing</p><p>Scan Form 16 Plumbing Sustainability</p> |  |  |  |  | 414 | 414 | 99 | [10 empty] | 194, 190, 197, 195
Do - Put Termite Sticker In MeterBox and Kitchen Cupboard | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 155 | TERMITE PROTECTION | 69 | [9 empty] | 210 | 210 | 99 | [10 empty] | 190
Req Light Fittings | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 164 | LIGHT FIT | 69 | [9 empty] | 379 | 379 | 99
Req Ceiling Insulation | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 169 | INSULATION | 69 |  | TRUE |  |  | <p>Scan Insulation Certificate</p> |  |  |  |  | 258 | 258 | 99 | [10 empty] | 197
Req Handrail installed to stairs | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 170 | STAIRS | 69 |  | TRUE | [7 empty] | 353 | 353 | 99 | [10 empty] | 197
Req Hot Water System | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 191 | PLUMBING FITOFF GEAR | 69 | [9 empty] | 363 | 363 | 99 | [10 empty] | 207SS
Req Plumber Fitoff Gear | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 191 | PLUMBING FITOFF GEAR | 69 | [9 empty] | 415 | 415 | 99 | [10 empty] | 207SS
Req Caulking Of External Expansion Joints | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 210 | WET SEAL | 69 | [9 empty] | 256 | 256 | 99 | [10 empty] | 197
Req Gapping To Skirting and Expansion Joints | Construction | Practical Completion | 2023-10-16 | 2023-10-16 | 1d | 106 | 248 | FINISHING TOUCHES | 69 | [9 empty] | 343 | 343 | 99 | [10 empty] | 214SS
Req Painter Touch Ups | Construction | Practical Completion | 2023-10-17 | 2023-10-17 | 1d | 106 | 100 | PAINTER | 69 | [9 empty] | 401 | 401 | 99 | [10 empty] | 203
Do Plumbing Final Inspection | Construction | Practical Completion | 2023-10-17 | 2023-10-17 | 1d | 106 | 106 | PRIVATE CERTIFIER | 69 | TRUE | [8 empty] | 189 | 189 | 99 | [10 empty] | 213
SPO - Insulation Spread Ceiling Insulation | Construction | Practical Completion | 2023-10-17 | 2023-10-17 | 1d | 106 | 169 | INSULATION | 69 | [9 empty] | 476 | 476 | 99 | [10 empty] | 210
Req NBN/OPTIC Fit Off | Construction | Practical Completion | 2023-10-18 | 2023-10-18 | 1d | 106 | 149 | TELSTRA | 69 | [9 empty] | 390 | 390 | 99 | [10 empty] | 220SS
Req Electrician - Fit Off | Construction | Practical Completion | 2023-10-18 | 2023-10-18 | 1d | 106 | 115 | ELECTRICAL | 69 | TRUE |  |  |  | <p>Scan Smoke Detector Certificate</p><p>Scan Exhaust Fans</p> |  |  |  |  | 314 | 314 | 99 | [10 empty] | 206, 209, 207
Req Tiler to Install Tiles Behind Toilet | Construction | Practical Completion | 2023-10-18 | 2023-10-19 | 2d | 106 | 238 | TILER | 69 | [9 empty] | 505 | 505 | 99 | [10 empty] | 207
Req NBN/OPTIC Commissioning | Construction | Practical Completion | 2023-10-19 | 2023-10-19 | 1d | 106 | 149 | TELSTRA | 69 |  |  |  |  | <p></p> |  |  |  |  | 389 | 389 | 99 | [10 empty] | 219
Req Air Conditioning Fit Off | Construction | Practical Completion | 2023-10-19 | 2023-10-19 | 1d | 106 | 185 | AIR CONDITIONING | 69 |  | TRUE | [7 empty] | 212 | 212 | 99 | [10 empty] | 220
Req Gas Fitoff | Construction | Practical Completion | 2023-10-19 | 2023-10-19 | 1d | 106 | 196 | GAS | 69 | TRUE | TRUE |  |  | <p>Scan Gas Compliance Certificate</p> |  |  |  |  | 347 | 347 | 99 | [10 empty] | 220
Req Solar Panel Commisions | Construction | Practical Completion | 2023-10-19 | 2023-10-19 | 1d | 106 | 333 | SOLAR | 69 | [9 empty] | 474 | 474 | 99 | [10 empty] | 220
Req Windows Cleaned Off Scaffold | Construction | Practical Completion | 2023-10-20 | 2023-10-20 | 1d | 106 | 137 | HOUSE CLEAN | 69 | [9 empty] | 539 | 539 | 99 | [10 empty] | 235SS -1d
Req Builders Clean | Construction | Practical Completion | 2023-10-20 | 2023-10-20 | 1d | 106 | 137 | HOUSE CLEAN | 69 |  | TRUE |  |  | <p>after internal fixout ready for floor coverings</p> |  |  |  |  | 239 | 239 | 99 | [10 empty] | 207, 223, 220
Req Privacy Screens (Supply and Install) | Construction | Practical Completion | 2023-10-20 | 2023-10-20 | 1d | 106 | 197 | PRIVACY SCREENS | 69 | [9 empty] | 427 | 427 | 99 | [10 empty] | 223, 220, 203, 207
Req Silicon Behind Toilet and Complete | Construction | Practical Completion | 2023-10-20 | 2023-10-20 | 1d | 106 | 210 | WET SEAL | 69 | [9 empty] | 449 | 449 | 99 | [10 empty] | 207, 221
Req Fly Screen | Construction | Practical Completion | 2023-10-23 | 2023-10-23 | 1d | 106 | 186 | TURN KEY | 69 | [9 empty] | 337 | 337 | 99 | [10 empty] | 226, 227
Req Security Screen Doors & Windows | Construction | Practical Completion | 2023-10-23 | 2023-10-23 | 1d | 106 | 186 | TURN KEY | 69 | [9 empty] | 443 | 443 | 99 | [10 empty] | 226, 227
Do Council Final Inspection | Construction | Practical Completion | 2023-10-23 | 2023-10-23 | 1d | 106 | 106 | PRIVATE CERTIFIER | 69 | TRUE |  |  |  | <p>Scan Council Final Inspction Report</p><p>Scan Council Final Certificate</p><p>Scan Application For An Occupation Certificate</p> |  |  |  |  | 178 | 178 | 99 | [10 empty] | 227, 205
Req Carpet | Construction | Practical Completion | 2023-10-23 | 2023-10-23 | 1d | 106 | 111 | FLOOR COVERINGS | 69 |  | TRUE | [7 empty] | 255 | 255 | 99 | [10 empty] | 227
Req Window Handover Service | Construction | Practical Completion | 2023-10-23 | 2023-10-23 | 1d | 106 | 103 | WINDOWS | 69 | [9 empty] | 537 | 537 | 99 | [10 empty] | 227
Req Full Turn Key Package | Construction | Practical Completion | 2023-10-23 | 2023-10-23 | 1d | 106 | 186 | TURN KEY | 69 |  | TRUE | TRUE |  | <p>Handover Audit Checklist - scan</p> |  |  |  |  | 342 | 342 | 99 | [10 empty] | 223, 220, 203, 207, 227
Req Window Coverings | Construction | Practical Completion | 2023-10-23 | 2023-10-23 | 1d | 106 | 186 | TURN KEY | 69 | [9 empty] | 536 | 536 | 99 | [10 empty] | 223, 220, 203, 207, 227
Do Finishing Touches | Construction | Practical Completion | 2023-10-24 | 2023-10-24 | 1d | 106 | 248 | FINISHING TOUCHES | 69 | [9 empty] | 183 | 183 | 99 | [10 empty] | 235
Req Builders Reclean | Construction | Practical Completion | 2023-10-25 | 2023-10-25 | 1d | 106 | 137 | HOUSE CLEAN | 69 |  |  |  |  | <p>ready for handover inspection</p> |  |  |  |  | 240 | 240 | 99 | [10 empty] | 232, 235, 237, 229
HANDOVER | Construction | Handover | 2023-10-26 | 2023-10-30 | 3d | 106 | [12 empty] | 624 | 624 | 99 |  | N/A | [8 empty] | 200
Do - Final Payment has been made, Organize Handover house | Construction | Handover | 2023-10-26 | 2023-10-26 | 1d | 106 | 117 | SUPERVISING | 69 | TRUE |  | TRUE |  | <p>supervisor does Final Payment has been made, Organize Handover house</p> |  |  |  |  | 198 | 198 | 99
Req Handover Clean | Construction | Handover | 2023-10-27 | 2023-10-27 | 1d | 106 | 137 | HOUSE CLEAN | 69 |  |  |  |  | <p>ready to hand over house</p> |  |  |  |  | 351 | 351 | 99 | [10 empty] | 240
Do Handover Of House | Construction | Handover | 2023-10-30 | 2023-10-30 | 1d | 106 | 117 | SUPERVISING | 69 | TRUE |  | TRUE |  | <p>Handover Of Keys , Remotes etc... Report </p><p>Disconnect Builders Power</p> |  |  |  |  | 595 | 595 | 99 | [10 empty] | 241
PRE CONSTRUCTIONS
Req 3D Drafting Qtys
Req Acoustic Report
Req BA - New Building Application
Req Build Over Sewer Application
Req Energy Efficient Rating
Req Eng Slab Design
Req Home Warranty Insurance
Req PLSL (QLeave)
Req Plumbing Approval
Req Soil Test & Wind Rating
Req Surveyed Plan Of Block
Req Tree Removal Application
Req Water Connection