## Tasks
Task Name | Predecessors | Duration | Start Date | Plan | Sales | Precon | Final Certificate | Site | Photo | Client | Client Photo | PO Required | Auto PO | Critical | Tags | Photo | Cert | Cert Lag | Manual | Multi | Order Time | Call Up | Plan
CREATE - Contract |  | 1d | 11 | No | No | No | No | No | Yes | No | Yes | Yes | Yes | No |  | Yes | Yes | 10 | No | No | No | No | No
DO - Load Invoices into XERO | 1 | 1d | 16 | No | No | No | No | No | No | No | No | Yes | Yes | Yes |  | No | No | 10 | No | No | No | No | No
GET - Finance Approval | 1 | 21d | 18 | No | No | No | No | No | No | No | No | Yes | No | No |  | No | No | 10 | No | No | No | No | No
CLAIM - DEPOSIT | 3 | 5d | 16 | No | No | No | No | No | No | No | No | No | No | No |  | No | No | 10 | No | No | No | No | No
ORDER - Soil Test and Wind Rating & Slab Design | 4 | 5d | 11 | No | No | No | Yes | No | No | Yes | No | No | No | No |  | No | Yes | 10 | No | No | No | No | No
ORDER - Contour Survey Plan | 4 | 5d
DO - Working Drawings | 4, 6 | 1d
DO - Plumbing Approval | 3, 4 | 1d
DO - QLeave | 3, 4 | 1d
DO - Hydraulics Design | 3, 4 | 1d
DO - Energy Efficiency | 3, 4 | 1d
CHECK - Land Settlement | 3, 4 | 1d
DO - Covenant Approval (if required) | 7 | 1d
DO - Certification | 8, 9, 10, 11 | 10d
DO - Driveway Application | 14 | 1d
Req Site Cut | 12, 14 | 1d
SLAB |  | 16d
Req Surveyor to Setout Wafflepod | 26 | 1d
Req Drainer for Drains Wafflepod | 28 | 2d
Req Electrician Underground (INC NBN) | 29SS | 1d
Req Power To Site | 30 | 10d
Req Concreter For Complete Slab Labour And Materials | 28, 29, 30 | 2d
Req Termite Protection Penetrations | 32SS | 1d
PHOTO - Slab | 32 | 1d
Req Waterproof Slab Edge | 32 | 1d
CLAIM - Slab | 32 | 5d
CERTIFICATE - Surveyor | 28FS +10d | 1d
CERTIFICATE - Engineer Slab | 32FS +10d | 1d
FRAME |  | 12d
Req Frame Hardware | 42SS -1d | 1d
Req Frame Material Ground Floor | 42SS -1d | 1d
Req Carpenter Ground Floor | 32FS +2d | 5d
Req Termite Perimeter | 42SS | 1d
Req Roof Trusses | 42SS +2d | 1d
Req Crane Roof Trusses | 44SS | 1d
Req Steel Posts | 44 | 1d
PHOTO - Frame | 42 | 1d
Do Frame Inspection | 42 | 1d
Req Partition Wall | 42 | 1d
CERTIFICATE - Engineer Frame INC Hoist | 48 | 1d
CERTIFICATE - Termite | 43FS +5d | 1d
CLAIM - Frame | 42, 47 | 5d
CERTIFICATE - Roof Trusses | 44FS +5d | 1d
ENCLOSED |  | 19d
Req Fascia and Gutter and Colorbond Roof | 42, 49 | 5d
Req External Doors | 55FF -1d | 1d
Req Windows | 55FF -1d | 1d
Req External Door Handle Locks | 56SS | 1d
Req Carpenter Install Windows/Doors | 42, 49, 57 | 1d
Req Carpenter Straighten Frame | 59SS | 1d
Req Mixer Bodies For Plumber Rough In | 68SS -1d | 1d
FIT - Window Actuators | 57, 59SS | 1d
Req Wall Sisilation Ground Floor | 59SS | 1d
Req Measure Garage Doors | 59 | 1d
Req Rough In Solar Panels | 55 | 1d
Req Air Conditioning Rough In | 55 | 1d
Req Electrician - Prewire | 55 | 3d
Req Plumber Rough In | 55 | 3d
Req Soffit Hardware and Cladding | 55 | 1d
Req Fire Rough In | 55 | 1d
Req Carpenter Soffits Ground Floor | 55, 69 | 2d
Req Install Ply to Bathrooms | 68 | 1d
Do Plumbing Rough-In Inspection | 68 | 1d
Req Carpenter Cladding | 71 | 5d
Do Inspection NDIS | 72 | 1d
PHOTO - Ply Bathrooms, Bedroom Crane Supports | 72 | 1d
CERTIFICATE - Windows | 57FS +5d | 1d
PHOTO - Enclosed | 74 | 1d
Req Down Pipes Ground Floor | 74 | 1d
CLAIM - Enclosed | 74, 78 | 5d
FIXING |  | 35d
Req Ceiling & Wall Insulation Before Plasterboard | 68, 67, 70, 66, 65 | 1d
Req Plaster Board | 73, 66, 67, 68, 82 | 7d
Req Internal Fixout | 85SS -1d | 1d
Req Carpenter Fixout | 83 | 2d
Req Garage Doors | 83 | 1d
SPO - Electrician - Cutouts | 83 | 1d
Req Internal Door Handles | 85SS | 1d
FIT - Auto Door Openers | 85 | 2d
Req Kitchen | 85 | 5d
Req Water Proofer | 85 | 2d
Req Tiles | 93SS -1d | 1d
Req Tiler | 90, 91 | 7d
SPO - Plaster Fit Cornice | 90 | 1d
CERTIFICATE - Waterproofer | 91FS +5d | 1d
Req Painter Internal House | 93 | 7d
Measure Shower Screens Book Fitting | 93 | 1d
Req Pre Paint (Including Sanding) | 96SS +1d | 2d
PHOTO - Fixing | 92, 96 | 1d
Req Painter External House | 96, 74, 79 | 2d
CLAIM - Fixing | 93, 96, 99 | 5d
DRIVEWAY |  | 4d
Req Driveway Kerb Cut Out | 106SS -2d | 1d
FIT - Drains to Front of Doors | 106SS -2d | 1d
Req Driveway Steel Reo | 106SS -1d | 1d
Req Driveway Concretor | 79, 93 | 1d
PHOTO - Driveway | 106 | 1d
LANDSCAPING |  | 8d
Req Retaining Wall | 106 | 2d
Req Fence | 109, 106 | 2d
Req Landscaping | 110 | 3d
PHOTO - Fence and Landscaping | 110, 111 | 1d
PRACTICAL COMPLETION |  | 15d
Req Hot Water System | 121SS -1d | 1d
Req Plumber Fitoff Gear | 121SS -1d | 1d
Req Fire System Fitoff | 96, 93 | 1d
Req Electrical Items | 127SS -1d | 1d
Req Vinyl Sliders | 96, 93 | 1d
Req Window Coverings | 96, 93 | 1d
Req Carpenter For Final Fitoff | 93, 96 | 1d
Req Plumber - Fit Off | 93, 96 | 2d
Req Shower Screens | 93, 96 | 1d
Req SAT System | 127SS -1d | 1d
CERTIFICATE - Fire Alarms | 116 | 1d
CERTIFICATE - Shower Screens | 122 | 1d
Do Finishing Touches | 120 | 5d
Req Electrician - Fit Off | 93, 96, 119 | 3d
Do Plumbing Final Inspection | 121 | 1d
Req Gapping To Skirting and Expansion Joints | 121, 120 | 1d
Req Air Conditioning Fit Off | 127FF -1d | 1d
GET - All Forms for Final Inspection | 145SS -5d | 1d
DO - Get Hot Water Rebate | 128 | 1d
Req Full Turn Key Package | 127, 121 | 1d
Req Painter Touch Ups | 121, 127, 118 | 1d
Req Solar Panel Commisions | 127 | 1d
CERTIFICATE - Electrician | 127 | 1d
Req Ceiling Insulation | 127, 135 | 1d
Req Vinyl Floor | 133 | 1d
Req Window Handover Service | 133 | 1d
SPO - Insulation Spread Ceiling Insulation | 127, 135 | 1d
Do - Put Termite Sticker In MeterBox and Kitchen Cupboard | 145SS -1d | 1d
Req Builders Clean | 127, 135, 138, 126 | 1d
CERTIFICATE - Ceiling Insulation | 137 | 1d
PHOTO - Practical Completion | 142 | 1d
Do Council Final Inspection | 142 | 1d
GET - Form 11/21 from Certifier | 145 | 1d
CREATE - Builder Confirmation | 145 | 1d
GET - Engineer For Future Ceiling | 145 | 1d
GET - SDA Site Density Report | 145 | 1d
CREATE - Evacuation Plan | 145 | 1d
CLAIM - Practical Completion | 145 | 5d
DO - NDIS Final Inspection | 145, 147, 150 | 1d
DO - Final Payment has been made, Organize Handover house | 145, 151 | 1d